## Release#5
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Points | Done |  |  |  | Day | Planned | Iteam | Comment | Total | Actual
1 | 17 | 14 | 200 |  |  |  | Update Product Test Cases | 0% | El-Gohary | 1 | 1 |  |  |  | 1 | 5 | Estmation for tasks | All Team | 17
2 | 44 | 51 |  |  |  |  | Update Shopping Cart Test Cases | 0% | El-Gohary | 1 | 1 |  |  |  |  | 1 | Update Product Test Cases | El-Gohary
3 | 70 | 70 |  |  |  |  | Update User Registration Test Cases | 0% | Fatma | 1 | 1 |  |  |  |  | 1 | Update Shopping Cart Test Cases | El-Gohary
4 | 95 | 95 |  |  |  |  | Update User Login Test Cases | 0% | Fatma | 1 | 1 | Comments | Sum of Points | Sum of Done |  | 1 | Update User Registration Test Cases | Fatma
5 | 119 | 119 |  |  |  |  | Update Checkout Test Cases | 0% | Ganna | 2 | 2 | All Team | 30 | 30 |  | 1 | Update User Login Test Cases | Fatma
6 | 129 | 129 |  |  |  |  | Update Admin Test Cases | 0% | Hager | 3 | 3 | El-Gohary | 33 | 33 |  | 2 | Update Checkout Test Cases | Ganna
[7 empty] | Update Supplier Test Cases | 0% | Ganna | 1 | 1 | Fatma | 15 | 15 |  | 3 | Update Admin Test Cases | Hager
[7 empty] | Update Test Cases for Profile & Order History | 0% | Hager | 2 | 2 | Ganna | 21 | 21 |  | 1 | Update Supplier Test Cases | Ganna
[7 empty] | Run Product Test Cases | 0% | El-Gohary | 4 | 4 | Hager | 27 | 27 |  | 2 | Update Test Cases for Profile & Order History | Hager
[7 empty] | Run Shopping Cart Test Cases | 0% | El-Gohary | 4 | 4 | Hazem | 3 | 3 | 2 | 4 | Run Product Test Cases | El-Gohary | 27
Risks | [6 empty] | Run User Registration Test Cases | 0% | Fatma | 2 | 2 | Grand Total | 129 | 129 |  | 4 | Run Shopping Cart Test Cases | El-Gohary
ID | Topic | Probability | Impact | Description | Handling | Actions | Run User Login Test Cases | 0% | Fatma | 2 | 2 |  |  |  |  | 2 | Run User Registration Test Cases | Fatma
R01 | Resources | high | high | Team capacity reduced from 6 to 5 members | Accept | - | Run Checkout Test Cases | 0% | Ganna | 3 | 3 |  |  |  |  | 2 | Run User Login Test Cases | Fatma
R02 | Resources | high | Medium | One member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer with daily online sessions and delegate critical tasks to other member | Run Admin Test Cases | 0% | Hager | 3 | 3 |  |  |  |  | 3 | Run Checkout Test Cases | Ganna
R03 | Resources | high | high | One member is in a Rehabilitation period post-surgery; full availability is not guaranteed. | Mitigate | Hiring new employees qualified | Run Supplier Test Cases | 0% | Ganna | 3 | 3 |  |  |  |  | 3 | Run Admin Test Cases | Hager
R04 | Technical | high | Medium | Technical gaps between members and shortage | Mitigate | Peer Review - Knowledge share | Run Test Cases for Profile & Order History | 0% | Hager | 3 | 3 |  |  |  |  | 3 | Run Supplier Test Cases | Ganna
R05 | Resources | Medium | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours | Execution Report | 0% | Hazem | 3 | 3 |  |  |  |  | 3 | Run Test Cases for Profile & Order History | Hager
[7 empty] | Document Bugs found in Registration | 0% | Fatma | 3 | 3 |  |  |  |  | 3 | Execution Report | Hazem
[7 empty] | Document Bugs found in Login | 0% | Fatma | 2 | 2 |  |  |  | 3 | 3 | Document Bugs found in Registration | Fatma | 26
[7 empty] | Document Bugs found in Product List | 0% | El-Gohary | 2 | 2 |  |  |  |  | 2 | Document Bugs found in Login | Fatma
[7 empty] | Document Bugs found in Cart | 0% | El-Gohary | 3 | 3 |  |  |  |  | 2 | Document Bugs found in Product List | El-Gohary
[7 empty] | Document Bugs found in Checkout | 0% | Ganna | 3 | 3 |  |  |  |  | 3 | Document Bugs found in Cart | El-Gohary
[7 empty] | Document Bugs found in Admin Dashboard | 0% | Hager | 3 | 3 |  |  |  |  | 3 | Document Bugs found in Checkout | Ganna
[7 empty] | Document Bugs found in Supplier Dashboard | 0% | Ganna | 3 | 3 |  |  |  |  | 3 | Document Bugs found in Admin Dashboard | Hager
[7 empty] | Document Bugs found in Profile & Order History | 0% | Hager | 7 | 7 |  |  |  |  | 3 | Document Bugs found in Supplier Dashboard | Ganna
[7 empty] | Fix Bugs | 0% | All Team | 25 | 25 |  |  |  |  | 7 | Document Bugs found in Profile & Order History | Hager
Issues | [6 empty] | Retest Product Test Cases | 0% | El-Gohary | 4 | 4 |  |  |  | 4 | 25 | Fix Bugs | All Team | 25
ID | Initiator | Probability | Impact | Description | Handling | Actions | Retest Shopping Cart Test Cases | 0% | El-Gohary | 4 | 4 |  |  |  | 5 | 4 | Retest Product Test Cases | El-Gohary | 24
I01 | Project Team | Actual | high | Current team capacity is 5 members, affecting the planned velocity. | Accept |  | Retest User Registration Test Cases | 0% | Fatma | 2 | 2 |  |  |  |  | 4 | Retest Shopping Cart Test Cases | El-Gohary
I02 | Project Team | Actual | high | one member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer | Retest User Login Test Cases | 0% | Fatma | 2 | 2 |  |  |  |  | 2 | Retest User Registration Test Cases | Fatma
I03 | Project Team | Actual | Medium | Observed technical gaps leading to slower delivery or quality issues. | Mitigate | Peer Review - Knowledge share- Hiring | Retest Checkout Test Cases | 0% | Ganna | 3 | 3 |  |  |  |  | 2 | Retest User Login Test Cases | Fatma
I04 | Project Team | Actual | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours | Retest Admin Test Cases | 0% | Hager | 3 | 3 |  |  |  |  | 3 | Retest Checkout Test Cases | Ganna
[7 empty] | Retest Supplier Test Cases | 0% | Ganna | 3 | 3 |  |  |  |  | 3 | Retest Admin Test Cases | Hager
[7 empty] | Retest Test Cases for Profile & Order History | 0% | Hager | 3 | 3 |  |  |  |  | 3 | Retest Supplier Test Cases | Ganna
[7 empty] | RTM | 0% | El-Gohary | 10 | 10 |  |  |  |  | 3 | Retest Test Cases for Profile & Order History | Hager
[7 empty] | Estmation for tasks | 100% | All Team | 5 | 5 |  |  |  | 6 | 10 | RTM | El-Gohary | 10
[9 empty] | Sum | 129 | 129 | [6 empty] | Sum | 129

## Release#4
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Points | Done |  |  |  | Day | Planned | Iteam | Comment | Total | Actual
1 | 18 | 13 | 90 |  |  |  | Update SIQ | 0% | El-Gohary | 4 | 4 |  |  |  | 1 | 5 | Estmation for tasks | All Team | 18 | 5
2 | 36 | 24 |  |  |  |  | Frontend — Registration | 100% | Hager | 4 | 4 |  |  |  |  | 4 | update SIQ | El-Gohary |  | 4
3 | 51 | 36 |  |  |  |  | Frontend — Login | 100% | Hager | 3 | 3 |  |  |  |  | 3 | Frontend — Login | Hager |  | 3
4 | 64 | 43 |  |  |  |  | Frontend — Customer orders | 0% | Jana | 2 | 2 | Comments | Sum of Points | Sum of Done |  | 2 | Backend — Choosing The Framework | Ganna & Hazem |  | 2
5 | 78 | 57 |  |  |  |  | Frontend — Home | 100% | Jana | 2 | 2 | El-Gohary | 4 | 4 |  | 2 | Frontend — landing | Jana |  | 4
6 | 89 | 64 |  |  |  |  | Frontend — Cart | 0% | Jana | 3 | 2 | Fatma | 18 | 18 |  | 2 | Frontend — Home | Jana |  | 4
7 | 89 | 89 |  |  |  |  | Frontend — Checkout | 0% | Jana | 1 | 2 | Ganna | 16 | 16 | 2 | 3 | Frontend — Admin product | Fatma | 18 | 8
[7 empty] | Frontend — landing | 100% | Jana | 2 | 2 | Ganna & Hazem | 2 | 2 |  | 4 | Frontend — Registration | Hager |  | 4
[7 empty] | Frontend — Supplier product | 50% | Hager | 4 | 4 | Hager | 17 | 17 |  | 3 | Frontend — Cart | Jana |  | 3
[7 empty] | Frontend — Supplier order | 50% | Hager | 4 | 4 | Hazem | 15 | 15 |  | 3 | Backend — Learn Flask | Hazem |  | 3
Risks | [6 empty] | Frontend — Supplier add product | 50% | Hager | 2 | 2 | Jana | 12 | 12 |  | 3 | Backend — Learn Flask | Ganna |  | 3
ID | Topic | Probability | Impact | Description | Handling | Actions | Frontend — Profile | 100% | Jana | 2 | 2 | Grand Total | 84 | 84 |  | 2 | Frontend — Profile | Jana |  | 2
R01 | Resources | high | high | Team capacity reduced from 6 to 5 members | Accept | - | Frontend — Admin product | 100% | Fatma | 3 | 3 |  |  |  | 3 | 3 | Frontend — Admin customer | Fatma | 15 | 3
R02 | Resources | high | Medium | One member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer with daily online sessions and delegate critical tasks to other member | Frontend — Admin customer | 100% | Fatma | 3 | 3 |  |  |  |  | 3 | Frontend — Admin add user | Fatma |  | 4
R03 | Resources | high | high | One member is in a Rehabilitation period post-surgery; full availability is not guaranteed. | Mitigate | Hiring new employees qualified | Frontend — Admin supplier | 100% | Fatma | 3 | 3 |  |  |  |  | 2 | Backend — Creating Database Tables (Attributes, Relationships) | Hazem |  | 4
R04 | Technical | high | Medium | Technical gaps between members and shortage | Mitigate | Peer Review - Knowledge share | Frontend — Admin add user | 100% | Fatma | 3 | 3 |  |  |  |  | 3 | Backend — Configure Database | Ganna |  | 3
R05 | Resources | Medium | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours | Frontend — Admin add product | 100% | Fatma | 3 | 3 |  |  |  |  | 2 | Frontend — Customer orders | Jana |  | 2
[7 empty] | Frontend — Admin Order | 100% | Fatma | 3 | 3 |  |  |  |  | 2 | Frontend — Supplier add product | Hager |  | 2
[7 empty] | Backend — Choosing The Framework | 100% | Ganna & Hazem | 2 | 2 |  |  |  | 4 | 4 | Frontend — Supplier product | Hager | 13 | 4
[7 empty] | Backend — Creating Database Tables (Attributes, Relationships) | 100% | Hazem | 2 | 2 |  |  |  |  | 3 | Frontend — Admin supplier | Fatma |  | 3
[7 empty] | Backend — Configure Database | 100% | Ganna | 3 | 3 |  |  |  |  | 3 | Backend — Supplier Endpoints | Ganna |  | 4
[7 empty] | Backend — Learn Flask | 100% | Ganna | 3 | 3 |  |  |  |  | 3 | Backend — Login & Register Endpoints (Session Based Auth) | Hazem |  | 4
[7 empty] | Backend — Learn Flask | 100% | Hazem | 3 | 3 |  |  |  | 5 | 7 | Backend — Admin Endpoints | Ganna | 14 | 10
[7 empty] | Backend — Login & Register Endpoints (Session Based Auth) | 100% | Hazem | 3 | 3 |  |  |  |  | 7 | Backend — Customers Endpoints | Hazem |  | 10
[7 empty] | Backend — Admin Endpoints | 100% | Ganna | 7 | 7 |  |  |  | 6 | 4 | Frontend — Supplier order | Hager | 11 | 5
[7 empty] | Backend — Customers Endpoints | 100% | Hazem | 7 | 7 |  |  |  |  | 3 | Frontend — Admin add product | Fatma |  | 4
Issues | [6 empty] | Backend — Supplier Endpoints | 100% | Ganna | 3 | 3 |  |  |  |  | 3 | Frontend — Admin Order | Fatma |  | 4
ID | Initiator | Probability | Impact | Description | Handling | Actions | Estmation for tasks | 100% | All Team | 5 | 5 |  |  |  |  | 1 | Frontend — Checkout | Jana |  | 1
I01 | Project Team | Actual | high | Current team capacity is 5 members, affecting the planned velocity. | Accept |  |  |  | Sum | 89 | 89 | [6 empty] | Sum | 89 | 112
I02 | Project Team | Actual | high | one member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer
I03 | Project Team | Actual | Medium | Observed technical gaps leading to slower delivery or quality issues. | Mitigate | Peer Review - Knowledge share- Hiring
I04 | Project Team | Actual | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours
[10 empty] | Comments | Count of Deliverable
[10 empty] | El-Gohary | 1
[10 empty] | Fatma | 6
[10 empty] | Ganna | 4
[10 empty] | Ganna & Hazem | 1
[10 empty] | Hager | 5
[10 empty] | Hazem | 4
[10 empty] | Jana | 6
[10 empty] | Grand Total | 27

## Release#3
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Points | Done |  |  |  | Day | Planned | Iteam | Comment | Total
1 | 13 | 7 | 95 |  |  |  | Update SIQ | 100% | Fatma | 2 | 2 |  |  |  | 1 | 2 | Update SIQ | Fatma | 13 | 5est+2siq
2 | 32 | 20 |  |  |  |  | Update CRS | 100% | Ganna | 2 | 2 |  |  |  |  | 3 | Update SRS | Ganna |  | 7erd+1.5checkout+2git+2git
3 | 60 | 49 |  |  |  |  | Update SRS | 100% | Ganna | 3 | 3 |  |  |  |  | 1.5 | Update User Registration Test Cases | Fatma |  | 2flow cart+2flow admin+ 3srs+1.5tc login+1.5tc register+10wireframe+3seq customer+2class+4global
4 | 72 | 65 |  |  |  |  | Update RTM | 100% | El-Gohary | 3 | 3 | Comments | Sum of Points | Sum of Done |  | 1.5 | Update User Login Test Cases | Fatma |  | 10class+1.5tc cart+1.5tc product+2flow check
5 | 86 | 80 |  |  |  |  | Update Product Test Cases | 100% | Fatma | 2 | 2 | El-Gohary | 14 | 14 |  | 5 | Estmation for tasks | All Team
6 | 93 | 93 |  |  |  |  | Update Shopping Cart Test Cases | 100% | Fatma | 2 | 2 | Fatma | 14 | 14 | 2 | 2 | ERD Diagram (Identify Entity) | El-Gohary | 19
[7 empty] | Update User Registration Test Cases | 100% | Fatma | 1.5 | 1.5 | Ganna | 18 | 18 |  | 2 | ERD Diagram (Identify Attributes) | El-Gohary
[7 empty] | Update User Login Test Cases | 100% | Fatma | 1.5 | 1.5 | Hager | 15 | 15 |  | 2 | Update Shopping Cart Test Cases | Fatma
[7 empty] | Update Checkout Test Cases | 100% | Hager | 2 | 2 | Hazem | 13 | 13 |  | 2 | Update Checkout Test Cases | Hager
[7 empty] | Update Admin Test Cases | 100% | Hager | 3 | 3 | Jana | 14 | 14 |  | 3 | Update Admin Test Cases | Hager
Risks | [6 empty] | Update Supplier Test Cases | 100% | Hager | 3 | 3 | Grand Total | 88 | 88 |  | 2 | Update Product Test Cases | Fatma
ID | Topic | Probability | Impact | Description | Handling | Actions | Customer Sequence Diagram | 100% | Ganna | 3 | 3 |  |  |  |  | 2 | Update CRS | Ganna
R01 | Resources | high | high | Team capacity reduced from 6 to 5 members | Accept | - | Admin Sequence Diagram | 100% | Ganna | 5 | 5 |  |  |  |  | 2 | Learn Git | Fatma
R02 | Resources | high | Medium | One member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer with daily online sessions and delegate critical tasks to other member | Supplier Sequence Diagram | 100% | Ganna | 5 | 5 |  |  |  |  | 2 | Learn Git | Fatma
R03 | Resources | high | high | One member is in a Rehabilitation period post-surgery; full availability is not guaranteed. | Mitigate | Hiring new employees qualified | WireFrame | 100% | Jana | 5 | 5 |  |  |  | 3 | 5 | Wireframe | Jana | 28
R04 | Technical | high | Medium | Technical gaps between members and shortage | Mitigate | Peer Review - Knowledge share | WireFrame | 100% | Hager | 5 | 5 |  |  |  |  | 5 | Wireframe | Jana
R05 | Resources | Medium | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours | Global View | 100% | Jana | 4 | 4 |  |  |  |  | 2 | Admin Flow Chart | El-Gohary
[7 empty] | ERD Diagram (Identify Entity) | 100% | El-Gohary | 2 | 2 |  |  |  |  | 2 | Cart Flow Chart | El-Gohary
[7 empty] | ERD Diagram (Identify Attributes) | 100% | El-Gohary | 2 | 2 |  |  |  |  | 3 | Customer Sequence Diagram | Ganna
[7 empty] | ERD Diagram (Relationships) | 100% | El-Gohary | 2 | 2 |  |  |  |  | 2 | Class Diagram (Identify Attributes) | Hazem
[7 empty] | Draw ERD Diagram | 100% | El-Gohary | 1 | 1 |  |  |  |  | 3 | Class Diagram (Identify Methods) | Hazem
[7 empty] | Class Diagram (Identify Attributes) | 100% | Hazem | 2 | 2 |  |  |  |  | 2 | ERD Diagram (Relationships) | El-Gohary
[7 empty] | Class Diagram (Identify Methods) | 100% | Hazem | 3 | 3 |  |  |  |  | 1 | Draw ERD Diagram | El-Gohary
[7 empty] | Class Diagram (Identify Relationships) | 100% | Hazem | 3 | 3 |  |  |  |  | 3 | Update Supplier Test Cases | Hager
[7 empty] | Draw Class Diagram | 100% | Hazem | 2 | 2 |  |  |  | 4 | 3 | Class Diagram (Identify Relationships) | Hazem | 12
[7 empty] | Registration Flow Chart | 100% | Fatma | 2 | 2 |  |  |  |  | 2 | Draw Class Diagram | Hazem
Issues | [6 empty] | Login Flow Chart | 100% | Fatma | 1 | 1 |  |  |  |  | 2 | Checkout Flow Chart | Jana
ID | Initiator | Probability | Impact | Description | Handling | Actions | Flow chart (Product flow for admin and supplier) | 100% | Hazem | 3 | 3 |  |  |  |  | 2 | Registration Flow Chart | Fatma
I01 | Project Team | Actual | high | Current team capacity is 5 members, affecting the planned velocity. | Accept |  | Cart Flow Chart | 100% | El-Gohary | 2 | 2 |  |  |  |  | 3 | Update RTM | El-Gohary
I02 | Project Team | Actual | high | one member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer | Checkout Flow Chart | 100% | Jana | 2 | 2 |  |  |  | 5 | 5 | Admin Sequence Diagram | Ganna | 14
I03 | Project Team | Actual | Medium | Observed technical gaps leading to slower delivery or quality issues. | Mitigate | Peer Review - Knowledge share- Hiring | Flow chart (Order management Flow for customer, supplier and admin) | 100% | Jana | 3 | 3 |  |  |  |  | 5 | Supplier Sequence Diagram | Ganna
I04 | Project Team | Actual | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours | Admin Flow Chart | 100% | El-Gohary | 2 | 2 |  |  |  |  | 4 | Global View | Jana
[7 empty] | Learn Git | 100% | Fatma | 2 | 2 |  |  |  | 6 | 1 | Login Flow Chart | Fatma | 7
[7 empty] | Learn Git | 100% | Hager | 2 | 2 |  |  |  |  | 3 | Flow chart (Product flow for admin and supplier) | Hazem
[7 empty] | Estmation for tasks | 100% | All Team | 5 | 5 |  |  |  |  | 3 | Flow chart (Order management Flow for customer, supplier and admin) | Jana
[9 empty] | Sum | 93 | 93 | [6 empty] | Sum | 93

## Release#2
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments | Points | Day | Planned | Iteam | Comment
1 | 11 | 4 | 50 |  |  |  | Updated CMP | 100% | Ganna | 1 | 1 | 11 | SIQ (2), CRS(1), CMP(1), Research RTM (5), Estmation(2) | Ganna, Fatma, Hager, Elgohary
2 | 11 | 4 |  |  |  |  | Updated SIQ | 100% | Ganna | 2 | 2 | 11 | - | -
3 | 20 | 6.5 |  |  |  |  | Updated CRS | 100% | Ganna | 1 | 3 | 20 | PD TC(2.5), Learn Git(4) - Checkout TC(2.5) | El-Gohary, Hager, Fatma
4 | 28.5 | 12.5 |  |  |  |  | Updated SRS | 100% | Hazem, Ganna | 6 | 4 | 28.5 | SRS(6), Admin TC(2.5) | Hager, Hazem
5 | 33.5 | 15 |  |  |  |  | Research for RTM | 100% | Hazem, Ganna | 5 | 5 | 33.5 | Shopping Cart TC(2.5), User Registration(2.5) | El-Gohary, Hager, Fatma
6 | 36.5 | 25 |  |  |  |  | RTM | 100% | Hazem | 3 | 6 | 41.5 | Login TC(2.5), Supplier TC(2.5) ,RTM(3) | Fatma, Hager, Hazem
7 | 41.5 | 41.5 |  |  |  |  | Product Display Test Cases | 100% | El-Gohary | 2.5
[7 empty] | Shopping Cart Test Cases | 100% | El-Gohary | 2.5
[7 empty] | User Registration Test Cases | 100% | Fatma | 2.5
[7 empty] | User Login Test Cases | 100% | Fatma | 2.5
Risks | [6 empty] | Learn Git | 100% | Fatma | 2
ID | Topic | Probability | Impact | Description | Handling | Actions | Checkout Test Cases | 100% | Hager | 2.5
R01 | Resources | high | high | Team capacity reduced from 6 to 5 members | Accept | - | Admin management Test Cases | 100% | Hager | 2.5
R02 | Resources | high | Medium | One member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer with daily online sessions and delegate critical tasks to other member | Supplier management Test Cases | 100% | Hager | 2.5
R03 | Resources | high | high | One member is in a Rehabilitation period post-surgery; full availability is not guaranteed. | Mitigate | Hiring new employees qualified | Learn Git | 100% | Hager | 2
R04 | Technical | high | Medium | Technical gaps between members and shortage | Mitigate | Peer Review - Knowledge share | Estmation for tasks | 100% | All Team | 2
R05 | Resources | Medium | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours |  |  | SUM | 41.5
Issues
ID | Initiator | Probability | Impact | Description | Handling | Actions
I01 | Project Team | Actual | high | Current team capacity is 5 members, affecting the planned velocity. | Accept
I02 | Project Team | Actual | high | one member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer
I03 | Project Team | Actual | Medium | Observed technical gaps leading to slower delivery or quality issues. | Mitigate | Peer Review - Knowledge share- Hiring
I04 | Project Team | Actual | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours

## Release#1
Day | Planned | Consumed | Team Availability |  |  |  | Deliverable | % Completed | Comments
1 | 6.6667 | 10 | 40 |  |  |  | CRS | 100% | Ganna
2 | 13.3333 | 10 |  |  |  |  | SIQ | 100% | Fatma, Hager, Ganna
3 | 20 | 20 |  |  |  |  | PMP | 100% | El-Gohary
4 | 26.6667 | 30 |  |  |  |  | Risk sheet | 100% | Hager
5 | 33.3333 | 30 |  |  |  |  | SRS | 100% | Hazem
6 | 40 | 40 |  |  |  |  | CMP | 100% | Fatma
Risks
ID | Topic | Probability | Impact | Description | Handling | Actions
R01 | Resources | high | high | Team capacity reduced from 6 to 5 members | Accept | -
R02 | Resources | high | Medium | One member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer with daily online sessions and delegate critical tasks to other member
R03 | Resources | high | high | One member is in a Rehabilitation period post-surgery; full availability is not guaranteed. | Mitigate | Hiring new employees qualified
R04 | Technical | high | Medium | Technical gaps between members and shortage | Mitigate | Peer Review - Knowledge share
R05 | Resources | Medium | high | Burnout due to ISTQB Exam Preparation | Mitigate | Provide flexible hours
Issues
ID | Initiator | Probability | Impact | Description | Handling | Actions
I01 | Project Team | Actual | high | Current team capacity is 5 members, affecting the planned velocity. | Accept
I02 | Project Team | Actual | high | one member is on medical rehabilitation; work is restricted to remote only. | Mitigate | Knowledge Transfer
I03 | Project Team | Actual | Medium | Observed technical gaps leading to slower delivery or quality issues. | Mitigate | Peer Review - Knowledge share- Hiring