## Test Report Summary
Test Summary Report
Project / Software | Clothing Platform
Environment | Development
Tester / Team | Testing Time
Metric | Count | Percentage | Category | Total Cases | Passed | Failed | Cancelled | Blocked | Pass %
Total Test Cases | 141 | 100% | Register Tests | 24 | 18 | 6 | 0 | 0 | 75
Passed | 102 | 72.34% | Login & Authentication | 17 | 15 | 2 | 0 | 0 | 88.2353
Failed | 36 | 25.53% | Admin Functionality | 26 | 19 | 7 | 0 | 0 | 73.0769
Blocked / Not Executed | 0 | 0% | Supplier Functionality | 15 | 14 | 1 | 0 | 0 | 93.3333
Skipped | 0 | 0% | Product Management | 21 | 18 | 3 | 0 | 0 | 85.7143
Cancelled | 1 | 0.7092% | Landing Tests | 7 | 0 | 7 | 0 | 0 | 0
|  |  | Cart Tests | 19 | 13 | 6 | 0 | 0 | 68.4211
|  |  | Checkout Tests | 11 | 4 | 6 | 1 | 0 | 36.3636
Defect Status | Count | Percentage | CustomerOrder Tests | 1 | 1 | 0 | 0 | 0 | 100
Open | 37 | 97.37% | Total | 141 | 102 | 38 | 1 |  | 72.3404
In Progress | 0 | 0%
Fixed (Ready for Retest) | 0 | 0%
Closed | 0 | 0%
Reopened | 0 | 0%
Rejected / Deferred | 1 | 2.632%
Total Defects | 38 | 100%

## CHK_TCS Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invalid | Environment | Pre-condition | Steps | Test Data | Expected Results | Actual result | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Execution_Status | Comment
TC_CHK_001 | Verify successful checkout with valid data (city, Address, Mobile phone of reciever, name's reciever, Email) | valid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City 6. Enter Address 7. Enter phone of reciever 8.Enter name of reciever 9. Click confirm Order button 10.redirect to home page | 1- Email: gohary@mail.com 2- password: 123456789 | user is redirected to home page and pop up message "Order is placed successfully" | no popup message |  | approved |  | SRS-FN- Checkout-001 | Functional | Hager Elwan | Failed
TC_CHK_002 | Validate that all checkout page input fields are labeled | valid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5.Observe all input fields on the checkout page 6.Check that each input field has a clear and visible label | 1- Email: gohary@mail.com 2- password: 123456789 | All input fields on the checkout page are displayed with correct, clear, and visible labels. | All input fields on the checkout page are displayed with correct, clear, and visible labels. |  | approved |  | SRS-FN- Checkout-001 | Functional | Hager Elwan | Passed
TC_CHK_003 | Verify City field is mandatory when left empty with other valid data | invalid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Leave City field empty 6. Enter Address 7. Enter phone of reciever 8.Enter name of reciever 9. Click confirm Order button | 1- Email: gohary@mail.com 2- password: 123456789 | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | approved |  | SRS-FN-Checkout-002 | Functional | Hager Elwan | Failed
TC_CHK_004 | Verify Address field is mandatory when left empty with other valid data | invalid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City 6. Leave Address field empty 7. Enter phone of reciever 8.Enter name of reciever 9. Click confirm Order button | 1- Email: gohary@mail.com 2- password: 123456789 | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | approved |  | SRS-FN-Checkout-002 | Functional | Hager Elwan | Failed
TC_CHK_005 | Verify name of reciever name field is mandatory when left empty with other valid data | invalid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field 6. Enter Address field 7. Enter phone of reciever 8.leave name of reciever empty 9. Click confirm Order button | 1- Email: gohary@mail.com 2- password: 123456789 | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | approved |  | SRS-FN-Checkout-002 | Functional | Hager Elwan | Failed
TC_CHK_006 | Verify phone of reciever phone field is mandatory when left empty with other valid data | invalid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field 6. Enter Address field 7. Leave phone of reciever 8.Enter name of reciever 9. Click confirm Order button | 1- Email: gohary@mail.com 2- password: 123456789 | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | approved |  | SRS-FN-Checkout-002 | Functional | Hager Elwan | Failed
TC_CHK_007 | Verify that the "Confirm Order" button is displayed and clickable to confirm the order | valid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field 6. Enter Address field 7. Enter phone of reciever 8.Enter name of reciever 9. Click confirm Order button | 1- Email: gohary@mail.com 2- password: 123456789 | The Confirm Order button is displayed on the checkout page and clickable when entered valid data | The Confirm Order button is displayed on the checkout page and clickable when entered valid data |  | approved |  | SRS-FN- Checkout-003 | Functional | Hager Elwan | Passed
TC_CHK_008 | Verify Cash on Delivery (COD) payment method is clearly displayed as text on checkout page | valid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5.Observe the payment method section on the is displayed as text checkout page | 1- Email: gohary@mail.com 2- password: 123456789 | The system clearly displays Cash on Delivery (COD) as the payment method on the checkout page | The system clearly displays Cash on Delivery (COD) as the payment method on the checkout page |  | approved |  | SRS-FN-Checkout-004 | Functional | Hager Elwan | Passed
TC_CHK_009 | Verify checkout requires login | invalid | Web / Chrome | open URL User is not logged in | 1. Select product from home page 2. Add product to cart 3. Try to proceed to checkout | 1- Email: gohary@mail.com 2- password: 123456789 | User is redirected to login page |  |  | cancelled |  | SRS-FN-Checkout-005 | Functional | Hager Elwan | cancelled
TC_CHK_010 | Verify confirmation email is sent to the customer after placing order | valid | Web / Chrome | open URL User logged in | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field empty 6. Enter Address field empty 7. Enter phone of reciever 8.Enter name of reciever empty 9. Click confirm Order button | 1- Email: gohary@mail.com 2- password: 123456789 | A confirmation email is sent to the customer after successful order placement |  |  | approved |  | SRS-FN-Checkout-006 | Functional | Hager Elwan | Failed
TC-Checkout-011 | Verify "Back to Cart" button is displayed on the checkout page and redirects user to the cart page when clicked | valid | Web/Chrome | Open URL, User is logged in and on checkout page | 1.Check that the "Back to Cart" button is displayed 2.Click on the "Back to Cart" button | 1- Email: gohary@mail.com 2- password: 123456789 | Back to Cart button is displayed and user is redirected to the cart page | Back to Cart button is displayed and user is redirected to the cart page |  | approved |  | SRS-FN-Checkout-007 | Functional | Hager Elwan | Passed
Count
11
Passed
4
Failed
6
Cancelled
1

## Admin_Tcs Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invaldi | Environment | Pre-condition | Steps | Test Data | Expected Results | Post Condition | Attachment | Requirement ID | Type | Tester | Comment | TC Status | Actual Condition
TC-Admin-001 | Verify admin can add a new product with valid data( product name, photo, description, price, stock avaliability and supplier id) | valid | Web application | Open URL, Admin is logged in | 1.click on actions 2.click add product 3.Enter valid product data 4.Click Save | product name: jacket photo: dress.jpg description: olive green jacket price:50 : stock avaliability:2 supplier id: 16 | Product is added successfully and redirect admin to dashboard | Product is created | N/A | SRS-FN-Admin-001 | Functional | Hager Elwan |  | failed | pop up appear with "please enter valid data"
TC-Admin-002 | Verify admin cannot add a new product with missing required data | invalid | Web/Chrome | Open URL, Admin is logged in | 1.click on actions section 2.Click Add product 3.Leave required fields empty 4.Click Save | product name: photo: dress.jpg description: olive green jacket price:50 : stock avaliability:2 supplier id: 16 | Product is not added and validation message is displayed "please enter the valid data" | No product is created | N/A | SRS-FN-Admin-001 | Functional | Hager Elwan | N/A | passed | Product is not added after litting product name empty and validation message is displayed "please enter the valid data"
TC-Admin-003 | Verify admin can remove an existing product | valid | Web/Chrome | Open URL, Admin is logged in | 1.click product 2.Select product 3.Click Remove 4.Confirm deletion | Existing product | Product is removed successfully | Product is deleted | N/A | SRS-FN-Admin-002 | Functional | Hager Elwan |  | failed | product didn't deleted and pop up message appear "are you sure? "
TC-Admin-004 | Verify admin can add new customer with valid data(name,password,email,role:customer) | valid | Web/Chrome | Open URL, Admin is logged in | 1.click on actions section 2.Click Add user 3.Enter valid data(name,email,pass) 4.click on customer radio button 5.Click Save | name: jana11 password: 123456789 email: janaahmedelsayed15@gmail.com role:custome | customer is added successfully and redirect admin to dashboard | cutomer is added to database | N/A | SRS-FN-Admin-003 | Functional | Hager Elwan |  | passed | customer added successfully
TC-Admin-005 | Verify admin can remove an existing customer | valid | Web/Chrome | Open URL, Admin is logged in | 1.click customer 2.Select customer 3.Click Remove 4.Confirm deletion | Existing customer | customer is removed successfully | customer is deleted | N/A | SRS-FN-Admin-003 | Functional | Hager Elwan | N/A | passed | customer deleted successfully
TC-Admin-006 | Verify system prevents creating duplicate customer account with same email | valid | Web/Chrome | Open URL, Admin is logged in and a customer account with the same email already exists | 1.click on actions section 2.Click Add user 3.Enter valid Username, existing Email, valid Password, and 4.click on customer radio button 5.Click Save | Existing customer email | System shows "Email already exists" message and customer account is not created | No duplicate customer account is created | N/A | SRS-FN-Admin-003 | Functional | Hager Elwan |  | failed | customer did't added but different pop up message appear "error creating user"
TC-Admin-007 | Verify admin can add new supplier with valid data(name,password,email,role:supplier) | valid | Web/Chrome | Open URL, Admin is logged in | 1.click on actions section 2.Click Add supplier 3.Enter valid data(name,password,email) 4.click on supplier radio button 5.Click Save | name: hager password:123456789 email:hagerhagora@gmail.com role:supplier | supplier is added successfullyand redirect admin to dashboard | supplier is created and added to database | N/A | SRS-FN-Admin-004 | Functional | Hager Elwan | N/A | passed | supplier added successfully and redirected to dashboard
TC-Admin-008 | Verify admin can remove an existing supplier | valid | Web/Chrome | Open URL, Admin is logged in | 1.click supplier 2.Select supplier 3.Click Remove 4.Confirm deletion | Existing supplier | supplier is removed successfully | supplier is deleted | N/A | SRS-FN-Admin-004 | Functional | Hager Elwan | N/A | passed | supplier deleted sccessfully
TC-Admin-009 | Verify system prevents creating duplicate supplier account with same email | valid | Web/Chrome | Open URL, Admin is logged in and a customer account with the same email already exists | 1.click on actions section 2.Click Add user 3.Enter valid Username, existing Email, valid Password, and 4.click on supplier radio button 5.Click Save | Existing supplier email | System shows "Email already exists" message and supplier account is not created | No duplicate customer account is created | N/A | SRS-FN-Admin-004 | Functional | Hager Elwan |  | failed | Supplier did't added but different pop up message appear "error creating user"
TC-Admin-010 | Verify admin can view customer list with each customer's name and email | valid | Web/Chrome | Open URL, Admin is logged in | 1.Navigate to dashbord 2.click customer |  | Customer list is displayed with each customer's name and email | Lists remain available for review | N/A | SRS-FN-Admin-005 | Functional | Hager Elwan | N/A | passed | Customer list is displayed with each customer's name and email
TC-Admin-011 | Verify admin can view supplier list with each supplier's name and email | valid | Web/Chrome | Open URL, Admin is logged in | 1.Navigate to dashbord 2.click supplier 3.validate that all requirments of the order displayed |  | supplier list displayed with each supplier's name and email | Lists remain available for review | N/A | SRS-FN-Admin-005 | Functional | Hager Elwan | N/A | passed | supplier list displayed with each supplier's name and email
TC-Admin-012 | Verify admin can view the product list showing product name,decription, image ,price quantity,supplier id for each product | valid | Web/Chrome | Open URL, Admin is logged in | 1.Navigate to dashbord 2.click supplier 3.validate that all requirments of the product displayed |  | product list is displayed with product name,decription, image ,price quantity,supplier id for each product | Lists remain available for review | N/A | SRS-FN-Admin-001 | Functional | Hager Elwan | N/A | failed | supplier id dosent appear
TC-Admin-013 | Verify admin can view the order list showing Order ID, Customer Name, and Supplier Name for each order | valid | Web/Chrome | Open URL, Admin is logged in | 1.Navigate to dashbord 2.click orders 3.validate that all requirments of the order displayed |  | Order list is displayed with Order ID, Customer Name, and Supplier Name for each order | Lists remain available for review | N/A | SRS-FN-Admin-006 | Functional | Hager Elwan | N/A | failed | all points appear with these extra points: total price and reciever
TC-Admin-014 | Verify admin can approve a supplier product submission | valid | Web/Chrome | Open URL, Admin is logged in | 1.Navigate dashboard 2.Select a pending product 3.Click Approve 4.Confirm action | Valid pending supplier product | Product submission is approved successfully | Product status is updated to Approved | N/A | SRS-FN-Admin-007 | Functional | Hager Elwan | N/A | passed
TC-Admin-015 | Verify admin can reject a supplier product submission | valid | Web/Chrome | Open URL, Admin is logged in | 1.Navigate dashboard 2.Select a pending product 3.Click reject 4.Confirm action | Valid pending supplier product | Product submission is rejected successfully | Product status is updated to Rejected | N/A | SRS-FN-Admin-007 | Functional | Hager Elwan | N/A | passed
TC-Admin-016 | Verify admin can view pending product submissions | valid | Web/Chrome | Open URL, Admin is logged in | 1.click products that apper on admin dashboard 2.click in Pending radio button | N/A | Pending product submissions are displayed | Pending submissions list is displayed | N/A | SRS-FN-Admin-007 | Functional | Hager Elwan |  | passed
TC-Admin-017 | Verify admin can approve a pending product submission | valid | Web/Chrome | Open URL, Admin is logged in | 1.click products that apper on admin dashboard 2.click in Pending radio button 3.Select a pending product 4.Click Approve | N/A | Product is approved successfully and moved to the live product list | Product is approved and saved in db | N/A | SRS-FN-Admin-007 | Functional | Hager Elwan |  | passed
TC-Admin-018 | Verify admin can reject a pending product submission | valid | Web/Chrome | Open URL, Admin is logged in | 1.click products that apper on admin dashboard 2.click in Pending radio button 3.Select a pending product 4.Click on delete icon | N/A | Product is rejected successfully and removed from the system | Product is rejected | N/A | SRS-FN-Admin-007 | Functional | Hager Elwan |  | passed
TC-Admin-019 | Verify admin can search for a product by name in dashboard | valid | Web/Chrome | Open URL, Admin is logged | 1.click on search bar 2.Enter a product name 3.Click Search button | Product name | Matching product is displayed in search results | Search results are displayed | N/A | SRS-FN-Admin-008 | Functional | Hager Elwan |  | passed
TC-Admin-020 | Verify system shows no product found message for non-matching product name | valid | Web/Chrome | Open URL, Admin is logged in | 1.click on search bar 2.Enter a non-existing product name in 3.Click Search button | Non-existing product name | No product found message is displayed | No matching product is displayed | N/A | SRS-FN-Admin-008 | Functional | Hager Elwan |  | failed | no message appear
TC-Admin-021 | Verify admin can filter products by status("Pending" or "Approved" or “All”.) | valid | Web/Chrome | Open URL, Admin is logged in | 1.click products 2.Select a product status filter 3.Check displayed products | N/A | Only products matching the selected status are displayed | Filtered products are displayed | N/A | SRS-FN-Admin-009 | Functional | Hager Elwan |  | passed | Filtered products are displayed
TC-Admin-022 | verify admin can back to dashboard when existing in add user with back button | valid | Web/Chrome | Open URL, Admin is logged in | 1.click on actions section 2.Click Add user 3.click back | N/A | admin back to dashboard | navigating dashboard | N/A | SRS-FN-Admin-010 | Functional | Hager Elwan |  | passed | admin in dashboard
TC-Admin-023 | verify admin can back to dashboard when existing in add product feature with back button | valid | Web/Chrome | Open URL, Admin is logged in | 1.click on actions 2.click add product 3.click back | N/A | admin back to dashboard | navigating dashboard | N/A | SRS-FN-Admin-011 |  |  |  | passed
TC-Admin-024 | Verify Profile page displays Admin Email and Username | valid | Web/Chrome | Open URL, User is logged in | 1.click on Profile 2.Check displayed account information(email and user name) | N/A | admin Email and Username are displayed correctly based on account registration data | Profile information is displayed | N/A | SRS-FN-Profile-001 | Functional | Hager Elwan |  | passed
TC-Admin-025 | Verify Admin can update username only from Profile page | valid | Web/Chrome | Open URL, User is logged in | 1.click on Profile page 2.Edit Username field 3.Enter a new username 4.Click Save | New valid username | Profile is updated successfully and the new username is displayed | Username is updated | N/A | SRS-FN-Profile-002 | Functional | Hager Elwan |  | passed
TC-Admin-026 | verify admin can logout after click on logout button | valid | Web/Chrome | Open URL, User is logged in | 1.click on Profile page 2.click logout button | N/A | admin logout successfully and redirect login page | redirect to login page | N/A | SRS-FN-Profile-003 | Functional | Hager Elwan |  | passed | admin redirect to login page after ckicking logout button
Count
26
Passed
19
Failed
7
0
Leave City empty 2. Enter Address 3. Click confirm Order

## CustomerOrder Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invaldi | Environment | Pre-condition | Steps | Test Data | Expected Results | Post Condition | Attachment | Requirement ID | Type | Tester | Comment | TC Status | Actual Result
TC-CustomerOrders-001 | Verify Customer can view his Orders | valid | Web application | Open URL, Customer is logged in | 1.click on Orders 2.Check displayed order information | prevoius orders exist | Order ID, Total Price, and Creation Date for each order. |  | N/A | SRS-FN-CustomerOrders-001 | Functional | El-Gohary |  | passed | order details appear such id,price, date
count
1
Passed
1
0
0

## Landing Test Cases Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invalid | Environment | Pre-condition | Steps | Test Data | Expected Results | Actual result | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Execution_Status | Comment
TC_Landing_001 | Verify Login & Sign-up presence | valid | Web Browser (Chrome) |  | open URL for landing page | url http://localhost:5000/ | Both "Login" and "Sign-up" buttons/links are visible in the navigation bar | Profile buttons still visible instead of Login/Sign-up button. |  | Ready | N/A | SRS-FN-Landing-001 | UI/Functional | Mahmoud | Failed
TC_Landing_002 | Verify Sign-up Navigation | valid | Web Browser (Chrome) |  | open URL for landing page Click on the "Sign-up" button. | url http://localhost:5000/ | The user is redirected to the Registration page. | No Registration button |  | Ready | N/A | SRS-FN-Landing-001 | Functional | Mahmoud | Failed
TC_Landing_003 | Verify login Navigation | valid | Web Browser (Chrome) |  | open URL for landing page Click on the "Login" button. | url http://localhost:5000/ | The user is redirected to the login page. | No Login button |  | Ready | N/A | SRS-FN-Landing-001 | Functional | Mahmoud | Failed
TC_Landing_004 | verify Add to Cart button shows a error message "Please login to add items to cart" | invalid | Web Browser (Chrome) |  | open URL for landing page Click on the "Add to Cart" button. | url http://localhost:5000/ | A message appears: "Please login to add items to cart" | A message appears: "Failed to add to cart" |  | Ready | N/A | SRS-FN-Landing-001 | Functional | Mahmoud | Failed
TC_Landing_005 | Verify Home button redirect to login page when user is logged out. | valid | Web Browser (Chrome) |  | open URL for landing page Ensure user is logged out. Click on the "Home" button. | url http://localhost:5000/ | User is redirected to the Login page. | redirected to /customer/ |  | Ready | N/A | SRS-FN-Landing-001 | Functional | Mahmoud | Failed
TC_Landing_006 | Verify Cart button redirect to login page when user is logged out. | valid | Web Browser (Chrome) |  | open URL for landing page Ensure user is logged out. Click on the "Cart" button. | url http://localhost:5000/ | User is redirected to the Login page. | redirected to /customer/cart |  | Ready | N/A | SRS-FN-Landing-001 | Functional | Mahmoud | Failed
TC_Landing_007 | Verify Order button redirect to login page when user is logged out. | valid | Web Browser (Chrome) |  | open URL for landing page Ensure user is logged out. Click on the "Order" button. | url http://localhost:5000/ | User is redirected to the Login page. | redirected to /customer/orders |  | Ready | N/A | SRS-FN-Landing-001 | Functional | Mahmoud | Failed
count
7
passed
0
failed
7
0

## Product Test Cases Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invalid | Environment | Pre-condition | Steps | Test Data | Expected Results | Actual result | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Execution_Status | Comment
TC_Product_001 | Verify product names are displayed. | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe product names | 1- Email: gohary@mail.com 2- password: 123456789 | Product names are clearly displayed for each product. | Product names are clearly displayed for each product. |  | Ready |  | SRS-FN-Product-001 | UI/Functional | Mahmoud | Passed
TC_Product_002 | Verify product images are displayed. | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe product images | 1- Email: gohary@mail.com 2- password: 123456789 | product images are clearly displayed for each product. | product images are clearly displayed for each product. |  | Ready |  | SRS-FN-Product-002 | UI/Functional | Mahmoud | Passed
TC_Product_003 | Verify product descriptions are displayed. | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe product descriptions | 1- Email: gohary@mail.com 2- password: 123456789 | Product descriptions are clearly visible below the product name. | Product descriptions are clearly visible below the product name. |  | Ready |  | SRS-FN-Product-003 | UI/Functional | Mahmoud | Passed
TC_Product_004 | Verify product prices are displayed with currency. | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe product prices | 1- Email: gohary@mail.com 2- password: 123456789 | Prices are displayed with "EGP" | Prices are displayed with "EGP" |  | Ready |  | SRS-FN-Product-004 | UI/Functional | Mahmoud | Passed
TC_Product_005 | Verify stock availability status is displayed. | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe stock status for each product | 1- Email: gohary@mail.com 2- password: 123456789 | Stock status shows "Stock: [n] items (In Stock) or (Out of Stock)" | Stock status shows "Stock: [n] items (In Stock) or (Out of Stock)" |  | Ready |  | SRS-FN-Product-005 | UI/Functional | Mahmoud | Passed
TC_Product_006 | Verify quantity selector UI elements are displayed. | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe quantity selector for a product | 1- Email: gohary@mail.com 2- password: 123456789 | Quantity selector shows "-" button, "1" as default value, and "+" button | Quantity selector shows "-" button, "1" as default value, and "+" button |  | Ready |  | SRS-FN-Product-006 | UI/Functional | Mahmoud | Passed
TC_Product_007 | Verify minimum quantity limit (cannot go below 1). | invalid | Web Browser (Chrome) | 1.Client has a valid account. 2. Product is in stock 3. Default quantity is 1 | 1. Log in with valid client credentials 2. Navigate to home page 3. Click minus (-) button for quantity selector | 1- Email: gohary@mail.com 2- password: 123456789 | Quantity value remains 1 and does not decrease. | Quantity value remains 1 and does not decrease. |  | Ready |  | SRS-FN-Product-006 | UI/Functional | Mahmoud | Passed
TC_Product_008 | Verify maximum stock limit for quantity selector. | invalid | Web Browser (Chrome) | 1.Client has a valid account. 2. Product has specific stock limit (e.g., stock = X) | 1. Log in with valid client credentials 2. Navigate to home page 3. Click plus (+) button repeatedly until reaching stock limit 4. Click plus (+) button again | 1- Email: gohary@mail.com 2- password: 123456789 | Quantity value stays at max stock (X) and does not exceed available stock. | Quantity value stays at max stock (X) and does not exceed available stock. |  | Ready |  | SRS-FN-Product-006 | UI/Functional | Mahmoud | Passed
TC_Product_009 | Verify UI elements for the Add to Cart button of the products are displayed for In Stock product | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe UI elements for the "Add to Cart" buttons of the In Stock products are displayed | 1- Email: gohary@mail.com 2- password: 123456789 | "Add to cart" button is visible, active | "Add to cart" button is visible, active |  | Ready |  | SRS-FN-Product-007 | UI/Functional | Mahmoud | Passed
TC_Product_010 | Verify UI elements for the supplier email of the products are displayed | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe UI elements for the supplier email of the products are displayed | 1- Email: gohary@mail.com 2- password: 123456789 | supplier email is displayed | supplier email is displayed |  | Ready |  | SRS-FN-Product-008 | UI/Functional | Mahmoud | Passed
TC_Product_011 | Verify Add to Cart button is enabled for in-stock products. | valid | Web Browser (Chrome) | Client has a valid account. | 1. Log in with valid client credentials 2. Navigate to home page 3. Observe Add to Cart button for an in-stock product | 1- Email: gohary@mail.com 2- password: 123456789 | Add to Cart button is enabled (clickable) | Add to Cart button is enabled (clickable) |  | Ready |  | SRS-FN-Product-007 | UI/Functional | Fatma | Passed
TC_Product_012 | Verify Add to Cart button is disappeared when product is Out of Stock. | invalid | Web Browser (Chrome) | 1.Client has a valid account 2. Product stock = 0 | 1. Log in with valid client credentials 2. Navigate to home page 3. Locate out-of-stock product 4. Observe Add to Cart button | 1- Email: gohary@mail.com 2- password: 123456789 | Add to Cart button is disappeared and displays text "Out of stock". | The 'Add to Cart' button is visible but disabled (not clickable). Additionally, faded UI effect to indicate the item is out of stock |  | Ready |  | SRS-FN-Product-007 | Functional | Fatma | Failed
TC_Product_013 | Verify In Stock status shows green color. | valid | Web Browser (Chrome) | 1.Client has a valid account 2. Product has stock greater than low stock threshold. | 1. Log in with valid client credentials 2. Navigate to home page 3. Locate an In Stock product 4. Observe the color of stock status | 1- Email: gohary@mail.com 2- password: 123456789 | Stock status displays "In Stock" with green color. | Stock status displays "In Stock" with green color. |  | Ready |  | SRS-FN-Product-005 | UI/Functional | Fatma | Passed
TC_Product_014 | Verify Out of Stock status shows red color. | valid | Web Browser (Chrome) | 1.Client has a valid account 2. Product stock = 0 | 1. Log in with valid client credentials 2. Navigate to home page 3. Locate an Out of Stock product 4. Observe the color of stock status | 1- Email: gohary@mail.com 2- password: 123456789 | Stock status displays "Out of Stock" with red color. | Stock status displays "Out of Stock" with red color. |  | Ready |  | SRS-FN-Product-005 | UI/Functional | Fatma | Passed
TC_Product_015 | Verify Add to Cart button adds product to cart with selected quantity. | valid | Web Browser (Chrome) | 1.Client has a valid account 2. Product is in stock | 1. Log in with valid client credentials 2. Navigate to home page 3. Select a product 4. Set quantity to X (e.g., 2) 5. Click Add to Cart button 6. Navigate to Cart page | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Success message :"Added to cart" 2. Product appears in cart with correct quantity 3. Cart total updates correctly |  |  | Ready |  | SRS-FN-Product-007 | Functional | Fatma | Passed
TC_Product_016 | Verify Search bar is visible and editable. | valid | Web Browser (Chrome) | 1.Client has a valid account | 1. Log in with valid client credentials 2. Navigate to home page 3. Locate the Search bar 4. Click inside the Search bar 5. Type a product name | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Search bar is clearly visible 2. Search bar is editable | 1. Search bar is clearly visible 2. Search bar is editable |  | Ready |  | SRS-FN-Product-009 | UI/Functional | Fatma | Passed
TC_Product_017 | Verify Search button is visible and clickable. | valid | Web Browser (Chrome) | Client has a valid account | 1. Log in with valid client credentials 2. Navigate to home page 3. Locate the Search button 4. Click on the Search button | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Search button is clearly visible 2. Search button is clickable | 1. Search button is clearly visible 2. Search button is clickable |  | Ready |  | SRS-FN-Product-009 | UI/Functional | Fatma | Passed
TC_Product_018 | Verify Search returns relevant products. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Home page contains products | 1. Log in with valid client credentials 2. Navigate to home page 3. Enter a product name from products list in Search bar 4. Click Search button | 1- Email: gohary@mail.com 2- password: 123456789 | Search results display products matching the entered name | Search results display products matching the entered name |  | Ready |  | SRS-FN-Product-009 | Functional | Fatma | Passed
TC_Product_019 | Verify Search does nothing when search bar is empty. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Home page contains products | 1. Log in with valid client credentials 2. Navigate to home page 3. Leave Search bar empty 4. Click Search button | 1- Email: gohary@mail.com 2- password: 123456789 | No search action is triggered | No search action is triggered |  | Ready |  | SRS-FN-Product-009 | Functional | Fatma | Passed
TC_Product_020 | Verify Search shows no results message for non-matching product name. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Home page contains products | 1. Log in with valid client credentials 2. Navigate to home page 3. Enter a non-existent product name in Search bar 4. Click Search button | 1- Email: gohary@mail.com 2- password: 123456789 | 1. No products displayed 2. Message displayed: "No products found" | 1. No products displayed 2. No Message displayed |  | Ready |  | SRS-FN-Product-009 | Functional | Fatma | Failed
TC_Product_021 | Verify unauthenticated user cannot add product to cart. | invalid | Web Browser (Chrome) | User is NOT logged in | 1. Open Home page (not logged in) 2. Select a product 3. Set quantity to X 4. Click Add to Cart | 1- Email: gohary@mail.com 2- password: 123456789 | Error message: "Please login to add items to cart" | Error message: "Failed to add to cart" |  | Ready |  | SRS-FN-Product-010 | Functional | Fatma | Failed
count
21
passed
18
failed
3
cancelled
0

## Login_Tcs_Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invaldi | Environment | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Execution Status | Comment
TC-Login-001 | Verify that user can navigate from Home page to Login page. | valid | Web/Chrome | User is on Home page. | 1. Open the Home page 2. Click on Login button | N/A | User is redirected to the Login page. | There is no login button appears in the home page. | User remains on Login page. | in review | N/A | SRS-FN-login-001 | Functional | Fatma | Failed | N/A
TC-Login-002 | Verify that Email field exists and is editable. | valid | Web/Chrome | 1. User is on Home page 2. Navigated to Login page | 1. Locate the Email field 2. Click inside the field 3. Type a valid Email | Email = fatma123@gmail.com | 1. Email field is displayed 2. Field is editable 3. Typed text appears correctly | 1. Email field is displayed 2. Field is editable 3. Typed text appears correctly | Email field contains "fatma@gmail.com" | in review | N/A | SRS-FN-login-001 | Functional | Fatma | Passed | N/A
TC-Login-003 | Verify that Password field exists and is editable. | valid | Web/Chrome | 1. User is on Home page 2. Navigated to Login page | 1. Locate the Password field 2. Click inside the field 3. Type a valid Password | Password = Pass@123 | 1. Password field is displayed 2. Field is editable 3. Typed text appears as masked (dots) by default | 1. Password field is displayed 2. Field is editable 3. Typed text appears as masked (dots) by default | Password field contains "Pass@1234" (masked) | in review | N/A | SRS-FN-login-001 | Functional | Fatma | Passed | N/A
TC-Login-004 | Verify that Submit button exists and is clickable. | valid | Web/Chrome | 1. User is on Home page 2. Navigated to Login page | 1. Locate the Submit button 2. Click on Submit button | N/A | 1. Submit button is displayed 2. Button is clickable | 1. Submit button is displayed 2. Button is clickable | Validation errors appear if fields are empty | in review | N/A | SRS-FN-login-001, SRS-FN-login-002 | Functional | Fatma | Passed | N/A
TC-Login-005 | Verify that user can successfully login as Client with valid credentials. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page 3.User has a registered account with role = Client | 1. Enter valid Email 2. Enter valid Password 3. Click Submit button | 1.fatma123@gmail.com 2.pass@123 | User is redirected to Home page | User is redirected to Home page | User is logged in as Client. | in review | N/A | SRS-FN-login-001, SRS-FN-login-002, SRS-FN-login-003 | Functional | Fatma | Passed | N/A
TC-Login-006 | Verify that user can successfully login as Supplier with valid credentials. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page 3.User has a registered account with role = Supplier | 1. Enter valid Email 2. Enter valid Password 3. Click Submit button | 1.Email = sup1@gmail.com 2.Password = supp@123 | User is redirected to supplier dashboard | User is redirected to supplier dashboard | User is logged in as Supplier. | in review | N/A | SRS-FN-login-001, SRS-FN-login-002, SRS-FN-login-003 | Functional | Fatma | Passed | N/A
TC-Login-007 | Verify that user can successfully login as Admin with valid credentials. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Enter valid Email 2. Enter valid Password 3. Click Submit button | 1.Email = admin@gmail.com 2.Password = admin@123 | User is redirected to admin dashboard | User is redirected to admin dashboard | User is logged in as Admin. | in review | N/A | SRS-FN-login-001, SRS-FN-login-002, SRS-FN-login-003 | Functional | Fatma | Passed | N/A
TC-Login-008 | Verify that validation error appears when Email field is empty. | invalid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Leave Email empty 2. Enter valid Password 3. Click Submit | 1. Leave Email empty 2.Password = supp@123 | 1.Error message: "Email is required" 2. No redirect occurs | 1.Error message: "Email is required" 2. No redirect occurs | User remains on Login page. Not logged in. | in review | N/A | SRS-FN-login-001, SRS-FN-login-004 | Functional | Fatma | Passed | N/A
TC-Login-009 | Verify that validation error appears when Password field is empty. | invalid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Enter valid Email 2. Leave Password empty 3. Click Submit | 1.fatma123@gmail.com 2. Leave Password empty | 1.Error message: "Password is required" 2. No redirect occurs | 1.Error message: "Password is required" 2. No redirect occurs | User remains on Login page. Not logged in. | in review | N/A | SRS-FN-login-001, SRS-FN-login-004 | Functional | Fatma | Passed | N/A
TC-Login-010 | Verify that validation error appears when both Email and Password are empty. | invalid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Leave Email empty 2. Leave Password empty 3. Click Submit | 1. Leave Email empty 2. Leave Password empty | 1.Error message: "Email is required" and "Password is required" 2. No redirect occurs | 1.Only one Error message: "Email is required" appears 2. No redirect occurs | User remains on Login page. Not logged in. | in review | N/A | SRS-FN-login-001, SRS-FN-login-004 | Functional | Fatma | Failed | N/A
TC-Login-011 | Verify that invalid credentials are rejected (wrong password). | invalid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page 3.User has a registered account with Email =fatma@gmail.com | 1. Enter valid Email 2. Enter wrong Password 3. Click Submit | 1. fatma123@gmail.com 2. Password=123456767 | 1.Error message: "Invalid email or password" 2. No redirect occurs | 1.Error message: "Invalid email or password" 2. No redirect occurs | User remains on Login page. Not logged in. | in review | N/A | SRS-FN-login-001, SRS-FN-login-003, SRS-FN-login-004 | Functional | Fatma | Passed | N/A
TC-Login-012 | Verify that invalid credentials are rejected (wrong email). | invalid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Enter email that does not exist in database 2. Enter any Password 3. Click Submit | 1. tweety@gmail.com 2. Password=pass@123 | 1.Error message: "Invalid email or password" 2. No redirect occurs | 1.Error message: "Invalid email or password" 2. No redirect occurs | User remains on Login page. Not logged in. | in review | N/A | SRS-FN-login-001, SRS-FN-login-003, SRS-FN-login-004 | Functional | Fatma | Passed | N/A
TC-Login-013 | Verify that invalid credentials are rejected (wrong email and wrong password). | invalid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Enter email that does not exist 2. Enter wrong Password 3. Click Submit | 1. tweety@gmail.com 2. Password=123456767 | 1.Error message: "Invalid email or password" 2. No redirect occurs | 1.Error message: "Invalid email or password" 2. No redirect occurs | User remains on Login page. Not logged in. | in review | N/A | SRS-FN-login-001, SRS-FN-login-003, SRS-FN-login-004 | Functional | Fatma | Passed | N/A
TC-Login-014 | Verify that Password field is masked by default. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Enter a Password in the Password field 2. Observe the field while typing and after typing | Password = Pass@1234 | Password appears as dots and not as plain text | Password appears as dots and not as plain text | Password remains masked. | in review | N/A | SRS-FN-login-001 | Functional | Fatma | Passed | N/A
TC-Login-015 | Verify that user can show and hide password. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Enter a Password in the Password field 2. Click the Show icon 3. Click the Hide icon | Password = Pass@1234 | 1. After clicking Show: Password becomes visible as plain text 2.After clicking Hide: Password becomes masked again | 1. After clicking Show: Password becomes visible as plain text 2.After clicking Hide: Password becomes masked again | Password field returns to masked state. | in review | N/A | SRS-FN-login-001 | Functional | Fatma | Passed | N/A
TC-Login-016 | Verify that user can navigate to Register page from Login page using "Sign up here" link. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. On Login page 2. Click on "Sign up here" link | N/A | User is redirected to Register page. | User is redirected to Register page. | User is on Register page. | in review | N/A | SRS-FN-login-001 | Functional | Fatma | Passed | N/A
TC-Login-017 | Verify that login is secure (no sensitive data in URL). | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Login page | 1. Enter valid Email and Password 2. Click Submit 3. Check the URL after submission | Email=fatma123@gmail.com Password=pass@123 | URL does NOT contain email or password parameters . | URL does NOT contain email or password parameters . | User is logged in. | in review | N/A | SRS-FN-login-001 | Functional | Fatma | Passed | N/A
invalid
count
17
passed
15
failed
2
0
Leave City empty 2. Enter Address 3. Click confirm Order

## Register_Tcs_Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invalid | Environment | Pre-condition | Steps | Test Data | Expected Results | Actual Results | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Execution_Status | N/A
TC-Register-001 | Verify that user can navigate from Home page to Register page. | valid | Web/Chrome | User is on Home page. | 1.Open the Home page. 2.Click on Register button. | N/A | User is redirected to Register page. | There is no register button appears in the home page. | User remains on Register page. | in review | N/A | SRS-FN-REGISTER-001 | Functional | Fatma | Failed | N/A
TC-Register-002 | Verify that username field exists and is editable. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Register page | 1. Locate the Username field 2. Click inside the field 3. Type a valid Username | Username = Fatma | 1.Username field is displayed 2. Field is editable 3.Typed text appears correctly | 1.Username field is displayed 2. Field is editable 3.Typed text appears correctly | Username field contains "Fatma" | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-004 | Functional | Fatma | Passed
TC-Register-003 | Verify that Email field exists and is editable. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Register page | 1. Locate the Email field 2. Click inside the field 3. Type a valid Email | Email = fatma@gmail.com | 1.Email field is displayed 2.Field is editable 3. Typed text appears correctly | 1.Email field is displayed 2.Field is editable 3. Typed text appears correctly | Email field contains "fatma@gmail.com" | in review | N/A | SRS-FN-REGISTER-001 | Functional | Fatma | Passed
TC-Register-004 | Verify that Password field exists and is editable. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Register page | 1. Locate the Password field 2. Click inside the field 3. Type a valid Password | Password = Pass@1234 | 1.Password field is displayed 2. Field is editable 3.Typed text appears as masked (dots) by default | 1.Password field is displayed 2. Field is editable 3.Typed text appears as masked (dots) by default | Password field contains "Pass@1234" (masked) | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-002, SRS-FN-REGISTER-005 | Functional | Fatma | Passed
TC-Register-005 | Verify that Confirm Password field exists and is editable. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Register page | 1. Locate the Confirm Password field 2. Click inside the field 3. Type a valid Confirm Password | Confirm Password = Pass@1234 | 1.Confirm Password field is displayed 2. Field is editable 3.Typed text appears as masked (dots) by default | 1.Confirm Password field is displayed 2. Field is editable 3.Typed text appears as masked (dots) by default | Confirm Password field contains "Pass@1234" (masked) | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-002 | Functional | Fatma | Passed
TC-Register-006 | Verify that Role (Client/Supplier) options exist and are selectable. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Register page | 1. Locate the Role options (Client and Supplier) 2. Click on Client option 3. Click on Supplier option | Role = Client then Supplier | 1.Both Client and Supplier options are displayed 2.Client option is clickable and selectable 3. Supplier option is clickable and selectable 4.Only one option can be selected at a time | 1.Both Client and Supplier options are displayed 2.Client option is clickable and selectable 3. Supplier option is clickable and selectable 4.Only one option can be selected at a time | one role is selected | in review | N/A | SRS-FN-REGISTER-003 | Functional | Fatma | Passed
TC-Register-007 | Verify that Submit button exists and is clickable. | valid | Web/Chrome | 1.User is on Home page 2.Navigated to Register page | 1. Locate the Submit button 2. Click on Submit button | N/A | 1.Submit button is displayed 2.Button is clickable | 1.Submit button is displayed 2.Button is clickable | Validation errors appear if fields are empty | in review | N/A | SRS-FN-REGISTER-006 | Functional | Fatma | Passed
TC-Register-008 | Verify that user can successfully register as client with valid data. | valid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select role = Client 6. Click Submit | 1.Username = FatmaYasser 2.Email = fatma@gmail.com 3.Password = Pass@123 4.Confirm Password = Pass@123 5.Role = Client | User is redirected to Login page. | User is redirected to Login page. | 1.User is on Login page. 2.Account is created in the database. | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-003, SRS-FN-REGISTER-004, SRS-FN-REGISTER-005, SRS-FN-REGISTER-006 | Functional | Fatma | Passed | N/A
TC-Register-009 | Verify that user can successfully register as supplier with valid data. | valid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select role = Supplier 6. Click Submit | 1.Username = FatmaYasserSup1 2.Email = sup1@gmail.com 3.Password = supp@123 4.Confirm Password = supp@123 5.Role = Supplier | User is redirected to Login page. | User is redirected to Login page. | 1.User is on Login page. 2.Account is created in the database. | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-003, SRS-FN-REGISTER-004, SRS-FN-REGISTER-005, SRS-FN-REGISTER-006 | Functional | Fatma | Passed | N/A
TC-Register-010 | Verify that validation error appears when password and confirm password do not match. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter a different Confirm Password 5. Select any role 6. Click Submit | 1.Username = FatmaYasser1 2.Email = fatma1@gmail.com 3.Password = Pass@123 4.Confirm Password = sup@123 5.Role = Client | 1.Error message " Password and confirm password do not match". 2.NO redirect occurs. | 1.Error message " Password and confirm password do not match". 2.NO redirect occurs. | 1.User remains on Register page. 2. No account is created in the database. | in review | N/A | SRS-FN-REGISTER-002 | Functional | Fatma | Passed | N/A
TC-Register-011 | Verify that validation error appears when Email is already exists. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. 3.Email: "fatma@gmail.com" already exists in database. | 1. Enter valid Username (3–50 characters) 2. Enter the exisiting Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select any role 6. Click Submit | 1.Username = FatmaYasser2 2.Email = fatma@gmail.com (already used) 3.Password = pass@123 4.Confirm Password = pass@123 5.Role = Client | 1.Error message " Email already exists". 2.NO redirect occurs. | 1.Different Error message " Email already registered". and it does not appear under the email field. 2.NO redirect occurs. | 1.User remains on Register page. 2. No account is created in the database. | in review | N/A | SRS-FN-REGISTER-007 | Functional | Fatma | Failed | N/A
TC-Register-012 | Verify that validation error appears when password length is less than 8 characters. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Enter Password with length <8 4. Enter matching Confirm Password 5. Select any role 6. Click Submit | 1.Username = FatmaYasser22 2.Email = fatma22@gmail.com 3.Password = Pass123 4.Confirm Password = pass123 5.Role = Client | 1.Error message " Password must be between 8 and 64 characters". 2.NO redirect occurs. | 1.Error message " Password must be between 8 and 64 characters". 2.NO redirect occurs. | 1.User remains on Register page. 2. No account is created in the database. | in review | N/A | SRS-FN-REGISTER-005 | Functional | Fatma | Passed | N/A
TC-Register-013 | Verify that validation error appears when password length exceeds 64 characters. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Enter Password with length >64 4. Enter matching Confirm Password 5. Select any role 6. Click Submit | 1.Username = FatmaYasser222 2.Email = fatma222@gmail.com 3.Password =65 character string 4.Confirm Password = 65 character string 5.Role = Client | 1.Error message " Password must be between 8 and 64 characters". 2.NO redirect occurs. | 1.Error message " Password must be between 8 and 64 characters". 2.NO redirect occurs. | 1.User remains on Register page. 2. No account is created in the database. | in review | N/A | SRS-FN-REGISTER-005 | Functional | Fatma | Passed | N/A
TC-Register-014 | Verify that password field is masked by default. | valid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Password (8–64 characters) 2.Observe while typing that password appears as dots. 3. Enter matching Confirm Password 4.Observe while typing that Confirm password appears as dots. | 1.Password = Pass@123 2.Confirm Password = Pass@123 | Password appears as dots and not as plain text. | Password appears as dots and not as plain text. | Password remains masked. | in review | N/A | SRS-FN-REGISTER-002 | Functional | Fatma | Passed | N/A
TC-Register-015 | Verify that user can show and hide password. | valid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Password (8–64 characters) 2.Click the show icon. 3.Click the hide icon. 4. Enter valid Confirm Password (8–64 characters) 5.Click the show icon. 6.Click the hide icon. | 1.Password = Pass@123 2.Confirm Password = Pass@123 | 1.After clicking Show: Password becomes visible as plain text 2.After clicking Hide: Password becomes masked again | 1.After clicking Show: Password becomes visible as plain text 2.After clicking Hide: Password becomes masked again | Password field returns to masked state. | in review | N/A | SRS-FN-REGISTER-002 | Functional | Fatma | Passed | N/A
TC-Register-016 | Verify that validation error appears when Username length is less than 3 characters. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter Username with length <3 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select role = Client 6. Click Submit | 1.Username = Fa 2.Email = fatma808@gmail.com 3.Password = Pass@123 4.Confirm Password = Pass@123 5.Role = Client | 1.Error message: "Username must be between 3 and 50 characters" 2.No redirect occurs. | 1.Error message: "Username must be between 3 and 50 characters" 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-004 | Functional | Fatma | Passed | N/A
TC-Register-017 | Verify that validation error appears when Username length exceeds 50 characters. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter Username with length >50 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select role = Client 6. Click Submit | 1.Username = 51 character string 2.Email = fatma88@gmail.com 3.Password = Pass@123 4.Confirm Password = Pass@123 5.Role = Client | 1.Error message: "Username must be between 3 and 50 characters" 2.No redirect occurs. | 1.Error message: "Username must be between 3 and 50 characters" 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-004 | Functional | Fatma | Passed | N/A
TC-Register-018 | Verify that validation error appears when Username field is empty. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Leave username field empty 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select role = Client 6. Click Submit | 1.leave username field empty 2.Email = fatma008@gmail.com 3.Password = Pass@123 4.ConfirmPassword = Pass@123 5.Role = Client | 1.Error message: "Username is required" 2.No redirect occurs. | 1.Different Error message: "Required fields missing" 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-004 | Functional | Fatma | Failed | N/A
TC-Register-019 | Verify that validation error appears when Password field is empty. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Leave password field empty 4.Enter valid confirm Password (8–64 characters) 5. Select role = Client 6. Click Submit | 1.Fatma 2.Email = fatma882@gmail.com 3. Leave password field empty 4.Confirm password=pass@123 5.Role = Client | 1.Error message: "Password is required" 2.No redirect occurs. | 1.Different Error message: "Required fields missing" under password field 2.Error message: "Password and Confirm Password do not match" under confirm password field 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-005 | Functional | Fatma | Failed | N/A
TC-Register-020 | Verify that validation error appears when Confirm Password field is empty. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3.Enter valid Password (8–64 characters) 4. Leave confirm password field empty 5. Select role = Client 6. Click Submit | 1.Fatma 2.Email = fatma882@gmail.com 3.Password=pass@123 4.Leave confirm Password field empty 5.Role = Client | 1.Error message: "Confirm Password is required" 2.No redirect occurs. | 1.Different Error message: "Required fields missing" 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-001, SRS-FN-REGISTER-005 | Functional | Fatma | Failed | N/A
TC-Register-021 | Verify that validation error appears when Email field is empty. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2. Leave Email field empty 3. Enter valid Password (8–64 characters) 4. Enter matching confirm Password 5. Select role = Client 6. Click Submit | 1.Fatma 2.LeaveEmail field empty 3.Password =pass@1234 4.Confirmation Password = Pass@1234 5.Role = Client | 1. Error message: "Email is required" 2.No redirect occurs. | 1.Different Error message: "Required fields missing" 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-001 | Functional | Fatma | Failed | N/A
TC-Register-022 | Verify that validation error appears when Email format is invalid (missing domain). | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2.Enter Email without domain 3. Enter valid Password (8–64 characters) 4. Enter a matching Confirmation Password 5. Select role = Client 6. Click Submit | 1.Fatma 2.fatma@ 3.Password =pass@123 4.Confirmation Password = Pass@123 5.Role = Client | 1. Error message: "Invalid email format" 2.No redirect occurs. | 1. Error message: "Invalid email format" 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-001 | Functional | Fatma | Passed | N/A
TC-Register-023 | Verify that validation error appears when no role is selected. | invalid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2.Enter a valid Email 3. Enter valid Password (8–64 characters) 4. Enter a matching Confirmation Password 5. Do not select any role 6. Click Submit | 1.Fatma 2.fatma@gmail.com 3.Password =pass@123 4.Confirmation Password = Pass@123 5.Do not select any role | 1. Error message: "Please select a role" 2.No redirect occurs. | 1. Error message: "Please select a role" 2.No redirect occurs. | 1.User remains on Register page. 2. No account is created. | in review | N/A | SRS-FN-REGISTER-003 | Functional | Fatma | Passed | N/A
TC-Register-024 | Verify that Submit button redirects to Login page after successful registration. | valid | Web/Chrome | 1.User is on Home page. 2.User is navigated to Register page. | 1. Enter valid Username (3–50 characters) 2.Enter a unique Email 3. Enter valid Password (8–64 characters) 4. Enter a matching Confirmation Password 5. Select role = Client 6. Click Submit | 1.Fatma 2.fatma28@gmail.com 3.Password =pass@123 4.Confirmation Password = Pass@123 5.Role = Client | User is redirected to the Login page | User is redirected to the Login page | 1.User is on Login page. 2.Account is created in the database. | in review | N/A | SRS-FN-REGISTER-006 | Functional | Fatma | Passed | N/A
count
24
passed
18
failed
6
cancelled
0
blocked
0

## Cart Test Cases Execution (hidden)
TesTCASE ID | Test Cases Title | valid/invalid | Environment | Pre-condition | Steps | Test Data | Expected Results | Actual result | Post Condition | TC Status | Attachment | Requirement ID | Type | Tester | Execution_Status | Comment
TC_Cart_001 | Verify that a registered user can access the shopping cart page | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in | 1. Log in with valid client credentials 2. Add at least one product to cart 3. Click on the "Cart" button | 1- Email: gohary@mail.com 2- password: 123456789 | Shopping Cart page opens successfully, displaying the user's selected items | Shopping Cart page opens successfully, displaying the user's selected items |  | Ready | N/A | SRS-FN-Cart-001 | UI/Functional | Mahmoud | Passed | N/A
TC_Cart_002 | Verify that products names are displayed correctly in the cart. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in | 1. Add two different products to cart 2. Click on the Cart button 3. Observe the product names displayed in cart | 1- Email: gohary@mail.com 2- password: 123456789 | The products names displayed in the cart matches the name shown on the Home Page. | The products names displayed in the cart matches the name shown on the Home Page. |  | Ready | N/A | SRS-FN-Cart-001 | UI/Functional | Mahmoud | Passed | N/A
TC_Cart_003 | Verify that unit price of the products are displayed correctly in the cart. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in | 1. Add two different products to cart 2. Click on the Cart button 3. Observe the unit price displayed for each product | 1- Email: gohary@mail.com 2- password: 123456789 | The products unit price displayed in the cart matches the unit price shown on the Home Page. | The products unit price displayed in the cart matches the unit price shown on the Home Page. |  | Ready | N/A | SRS-FN-Cart-001/ SRS-FN-Cart-002 | UI/Functional | Mahmoud | Passed | N/A
TC_Cart_004 | Verify that the quantity of the products are displayed correctly in the cart.. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in | 1. Add two different products to cart (default quantity = 1) 2. Click on the Cart button 3. Observe the quantity displayed for each product | 1- Email: gohary@mail.com 2- password: 123456789 | Quantity displayed is 1 for each product | Quantity displayed is 1 for each product |  | Ready | N/A | SRS-FN-Cart-001/ SRS-FN-Cart-002 | UI/Functional | Mahmoud | Passed | N/A
TC_Cart_005 | Verify subtotal price calculation for each product. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in | 1. Add Product A (price x EGP) with quantity x 2. Add Product B (price x EGP) with quantity x 3. Click on the Cart button 4. Calculate: Subtotal = Unit Price × Quantity | 1- Email: gohary@mail.com 2- password: 123456789 | Subtotal = Quantity × Unit Price for each item Displayed subtotal value is correct | Subtotal = Quantity × Unit Price for each item Displayed subtotal value is correct |  | Ready | N/A | SRS-FN-Cart-001 | Functional | Mahmoud | Passed | N/A
TC_Cart_006 | Verify Total Price Calculation (subtotal + shipping). | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in | 1. Add Product A (x EGP) with quantity 2 (subtotal = x) 2. Add Product B (x EGP) with quantity 1 (subtotal = x) 3. Click on the Cart button 4. Calculate: Total = Sum of subtotals + Shipping fees (x EGP) | 1- Email: gohary@mail.com 2- password: 123456789 | Total price = sum of(Subtotal) + Shipping Fees Displayed total price value is correct | Total price = sum of(Subtotal) Displayed total price value is correct |  | Ready | N/A | SRS-FN-Cart-001 | Functional | Mahmoud | Failed | N/A
TC_Cart_007 | Verify success message is displayed after adding item to cart | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Product is available in stock | 1. Select any product 2. Click Add to Cart button | 1- Email: gohary@mail.com 2- password: 123456789 | popup success message is displayed "Added to cart" | popup success message is displayed "Added to cart" |  | Ready | N/A | SRS-FN-Cart-001 | UI/Functional | Mahmoud | Passed | N/A
TC_Cart_008 | Verify that adding the same product multiple times increases its quantity in the cart | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Product is available in stock with quantity > 1 | 1. Select a product 2. Click on "Add to Cart" button 3. Navigate to the cart page (Note the product quantity (should be 1)) 4. Go back to the product page 5. Click on "Add to Cart" again for the same product 6. Navigate to the cart page | 1- Email: gohary@mail.com 2- password: 123456789 | The product appears as a single item in the cart The product quantity is increased correctly (from 1 to 2) | The product appears as a single item in the cart The product quantity is increased correctly (from 1 to 2) |  | Ready | N/A | SRS-FN-Cart-002 | Functional | Mahmoud | Passed | N/A
TC_Cart_009 | Verify minimum quantity limit (cannot go below 1). | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Cart contains product with quantity = 1 | 1. Add a product to cart 2. Navigate to Cart page 3. Click minus (-) button for quantity selector | 1- Email: gohary@mail.com 2- password: 123456789 | The quantity value remains 1 and does not decrease. | The quantity value remains 1 and does not decrease. |  | Ready | N/A | SRS-FN-Cart-002 | Functional | Mahmoud | Passed | N/A
TC_Cart_010 | Verify Maximum Stock Limit for Order Quantity on Cart page | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Product is available in stock with quantity above 1 | 1. Add a product to cart 2. Navigate to Cart page 3. Click plus (+) button repeatedly until reaching stock limit | 1- Email: gohary@mail.com 2- password: 123456789 | The quantity value stays at max stock quantity and does not exceed the available stock. | The quantity value stays at max stock quantity and does not exceed the available stock. Popup message is displayed "Insufficient stock" |  | Ready | N/A | SRS-FN-Cart-002 | Functional | Mahmoud | Failed | N/A
TC_Cart_011 | Verify that clicking the trash icon removes the item from the cart | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Cart is empty | 1. Add a product to cart 2. Navigate to Cart page 3. Click trash icon for that product | 1- Email: gohary@mail.com 2- password: 123456789 | The selected item is removed from the cart Cart updates immediately without refresh | The selected item is removed from the cart after refresh |  | Ready | N/A | SRS-FN-Cart-003 | Functional | Mahmoud | Failed | N\A
TC_Cart_012 | Verify that total price updates automatically after removal | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Cart contains multiple products | 1. Add two products to cart 2. Navigate to Cart page and note total price 3. Click trash icon for one product | 1- Email: gohary@mail.com 2- password: 123456789 | The selected item is removed from the cart The cart total price is updated immediately without page refresh. The total price reflects the sum of remaining items only. | The selected item is removed from the cart The cart total price is updated immediately without page refresh. The total price reflects the sum of remaining items only. |  | Ready | N/A | SRS-FN-Cart-003 | Functional | Mahmoud | Passed | N/A
TC_Cart_013 | Verify Checkout button is clickable on the shopping cart page after added product. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Cart contains at least one product | 1. Add a product to cart 2. Navigate to Cart page 3. Observe Checkout button | 1- Email: gohary@mail.com 2- password: 123456789 | Checkout button is displayed and clickable on the Shopping Cart page | Checkout button is displayed and clickable on the Shopping Cart page |  | Ready | N/A | SRS-FN-Cart-004 | Functional | Mahmoud | Passed | N/A
TC_Cart_014 | Verify that the checkout Button is disabled when the cart is empty | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Cart is empty | 1. Navigate to the cart page | 1- Email: gohary@mail.com 2- password: 123456789 | Checkout button is disabled on the Shopping Cart page | Checkout button is enabled on the Shopping Cart page |  | Ready | N/A | SRS-FN-Cart-004 | Functional | Mahmoud | Failed | N/A
TC_Cart_015 | Verify that the checkout Button redirects user to checkout page | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Cart contains at least one product | 1. Add a product to cart 2. Navigate to Cart page 3. Click Checkout button | 1- Email: gohary@mail.com 2- password: 123456789 | User is successfully redirected to the Checkout page Checkout page is loaded without errors Correct checkout page layout is displayed | User is successfully redirected to the Checkout page Checkout page is loaded without errors Correct checkout page layout is displayed |  | Ready | N/A | SRS-FN-Cart-004 | Functional | Mahmoud | Passed | N/A
TC_Cart_016 | Verify that the Home Button redirects user to home page | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. User is on Cart page | 1. Add a product to cart 2. Navigate to Cart page 3. Locate the Home button 4. Click on the Home button | 1- Email: gohary@mail.com 2- password: 123456789 | User is successfully redirected to the Home page Home page is loaded without errors Correct home page layout is displayed | User is successfully redirected to the Home page Home page is loaded without errors Correct home page layout is displayed |  | Ready | N/A | SRS-FN-Cart-004 | Functional | Fatma | Passed | N/A
TC_Cart_017 | Verify that Home button is visible on Cart page. | valid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in | 1. Navigate to Cart page 2. Observe the page layout | 1- Email: gohary@mail.com 2- password: 123456789 | Home button is clearly visible on Cart page | Home button is clearly visible on Cart page |  | Ready | N/A | SRS-FN-Cart-004 | UI/Functional | Fatma | Passed | N/A
TC_Cart_018 | Verify that out-of-stock product in cart is handled correctly. | invalid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Product was in stock when added to cart 4. Product becomes out of stock before checkout | 1. Add a product with quantity 1 to cart (stock was available) 2. Navigate to Cart page and note product is visible 3. open with other user and add a product with all quantities 4. click checkout button 5. fill all fields with valid data 6. return to first user 7. Open cart | 1- Email: gohary@mail.com 2- password: 123456789 3- Email: ganna101@example.com 4- password: 12345689 | 1. Out of stock Product is removed from cart 2. Product's subtotal is removed 3. Total price updates correctly | Out of stock Product still in cart |  | Ready | N/A | SRS-FN-Cart-005 | Functional | Fatma | Failed | N/A
TC_Cart_019 | Verify cart quantity adjusts if stock decreases below ordered quantity. | invalid | Web Browser (Chrome) | 1. Client has a valid account 2. Client is logged in 3. Product has stock = X 4. Client added quantity Y to cart (Y ≤ X) 5. Stock decreases to below Y before checkout | 1. Add product with quantity Y to cart (stock was X) 2. Navigate to Cart page and note product is visible 3. open with other user and add a product with all quantities 4. click checkout button 5. fill all fields with valid data 6. return to first user 7. Navigate to Cart page | 1- Email: gohary@mail.com 2- password: 123456789 3- Email: ganna101@example.com 4- password: 12345689 | 1. Cart quantity is automatically reduced to available stock 2. Subtotal and total price update correctly | Cart quantity isn't reduced to available stock automatically |  | Ready | N/A | SRS-FN-Cart-005 | Functional | Fatma | Failed | N/A
count
19
passed
13
failed
6
0

## Supplier_Tcs Execution (hidden)
TesTCASE ID | Test Cases Title | Pre-condition | Steps | Test Data | Expected Results | Post Condition | Actual Results | Status | Comment | Requirement ID | Type | Executed by | Created by | Environment
TC-Supplier-001 | Verify supplier can access Add Product form from dashboard | Open URL, Supplier is logged in | 1.Click on Add Product from supplier dashboard | N/A | Add Product form is opened successfully | Add Product form is displayed | Supplier opened Add Product form successfully | Pass | No comment | SRS-FN-Supplier-001 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-002 | Verify Add Product form contains all required fields (Product Name, Description, Unit Price (EGP), Photo URL or Filename and Stock Quantity) | Open URL, Supplier is logged in | 1.Click on Add Product 2.Check displayed fields | N/A | Product Name, Description, Unit Price (EGP), Photo URL or Filename and Stock Quantity fields are displayed | Add Product form is displayed | Product Name, Description, Unit Price (EGP), Photo URL or Filename and Stock Quantity fields are displayed successfully | Pass | No comment | SRS-FN-Supplier-001 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-003 | Verify supplier can submit a new product with valid data(Product Name, Description, Unit Price (EGP), Photo URL or Filename and Stock Quantity) and product is saved with Pending status | Open URL, Supplier is logged in | 1.Click on Add Product 2.Enter valid product photo, name, description, stock quantity, and price 3.Click Submit | Valid product data | Product is submitted successfully and saved with status Pending | New product is created with Pending status | Product is submitted successfully with status Pending and Appeared in Product list | Pass | No comment | SRS-FN-Supplier-001 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-004 | Verify supplier cannot add a new product with missing required fields | Open URL, Supplier is logged in | 1.Click on Add Product 2.Leave one or more required fields empty 3.Click Submit | Missing photo or name or price | System shows validation message "please enter the required data" and product is not submitted | Product is not created | System shows "Enter Valid Data" instead of "please enter the required data" | Fail | change the text in message | SRS-FN-Supplier-001 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-005 | Verify supplier can remove their own product | Open URL, Supplier is logged in | 1.Click product list 2.Select one of the products 3.Click Remove 4.Confirm deletion | Existing product owned by supplier | Product is removed successfully | Product is deleted from list | Product was removed successfully and no longer appears in the product list | Pass | No comment | SRS-FN-Supplier-002 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-006 | Verify supplier can view it's own orders | Open URL, Supplier is logged in | 1.click orders |  | display all orders that requested from supplier | orders list open | display all orders that requested from supplier | Pass |  | SRS-FN-Supplier-003 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-007 | Verify supplier can view Order ID and Customer Name for each order related to their products | Open URL, Supplier is logged in and has products in orders | 1.click orders 2.Open an order related to supplier products 3.Check displayed order information | N/A | Order ID and Customer Name are displayed for the selected order | Order details are displayed to supplier | Order ID and Customer Name are displayed for the selected order | Pass |  | SRS-FN-Supplier-003 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-008 | Verify product status filters are displayed(Approved, Pending, or All) | Open URL, Supplier is logged in | 1.click products 2.Check product filters | N/A | Approved, Pending, and All filters are displayed | Filters are displayed | Approved, Pending, and All filter options were displayed on the products page | Pass | No comment | SRS-FN-Supplier-004 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-009 | Verify all supplier products are displayed by default when clicking the Products button | Open URL, Supplier is logged in and has multiple products with different statuses | 1.click products that display on supplier's dashboard | N/A | All supplier products are displayed by default | all product list is displayed | All supplier products were displayed by default | Pass | No comment | SRS-FN-Supplier-004 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-010 | Verify supplier can filter products by status | Open URL, Supplier is logged in | 1.click products 2.Select a product status filter 3.Check displayed products | N/A | Only products matching the selected status are displayed | Filtered products are displayed | Only products matching the selected status were displayed correctly | Pass | No comment | SRS-FN-Supplier-004 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-011 | Verify supplier can search for products by name in supplier dashboard | Open URL, Supplier is logged in | 1.Click on search bar in supplier dashboard 2.Enter product name in search field 3.Click Search button | Product name | Matching products are displayed in the search results | Search results are displayed | Matching products were displayed in search results after clicking the Search button | Pass | No comment | SRS-FN-Supplier-005 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-012 | Verify system shows "no product found" message for non-matching product name | Open URL, Supplier is logged in | 1.Click on search bar in supplier dashboard 2.Enter a non-existing product name in search field 3.Click Search button | Non-existing product name | No product found message is displayed | No matching products are displayed | "No product found" message was displayed for the non-existing product name | Pass | No comment | SRS-FN-Supplier-005 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-013 | Verify search does not work when search field is empty | Open URL, Supplier is logged in | 1.Leave search field empty 2.Click Search button | Empty search field | No search action is triggered | Product list remains unchanged | No search action was triggered and the product list remained unchanged | Pass | No comment | SRS-FN-Supplier-005 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-014 | Verify Profile page displays supplier Email and Username | Open URL, User is logged in | 1.click on Profile 2.Check displayed account information(email and user name) | N/A | User's Email and Username are displayed correctly based on account registration data | Profile information is displayed | Supplier's Email and Username were displayed correctly on the Profile page | Pass | No comment | SRS-FN-Profile-001 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
TC-Supplier-015 | Verify Supplier can update username only from Profile page | Open URL, User is logged in | 1.click on Profile page 2.Edit Username field 3.Enter a new username 4.Click Save | New valid username | Username is updated successfully and the new username is displayed | Username is updated | Username was updated successfully and the new username was displayed on the Profile page | Pass | No comment | SRS-FN-Profile-002 | Functional | Ganna Adel | Hager Elwan | Web/Chrome
COUNT
15
passed
14
failed
1
cancelled
0
blocked
0

## Bug Report (hidden)
Defect_ID | Defect Title | Pre-condition | Test Data | Steps | valid/invalid | Environment | Post-condition | Expected Result | Actual Results | Attachment | Priority | Severity | Test Case ID | Requirement ID | Type | Defect Status | Created by | Comment
Defect_Product_001 | The 'Add to Cart' button not disappeared for 'Out of Stock' Product | 1.Client has a valid account 2. Product stock = 0 | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Log in with valid client credentials 2. Navigate to home page 3. Locate out-of-stock product 4. Observe Add to Cart button | invalid | Web Browser (Chrome) |  | Add to Cart button is disappeared and displays text "Out of stock". | The 'Add to Cart' button is visible but disabled (not clickable). Additionally, faded UI effect to indicate the item is out of stock |  | Medium | Low | TC_Product_012 | SRS-FN-Product-007 | Functional | Fix | Mahmoud
Defect_Product_002 | "No products found" message not displayed on Search result for non-matching product name | 1. Client has a valid account 2. Home page contains products | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Log in with valid client credentials 2. Navigate to home page 3. Enter a non-existent product name in Search bar 4. Click Search button | valid | Web Browser (Chrome) |  | 1. No products displayed 2. Message displayed: "No products found" | No products displayed No Message displayed |  | Medium | Low | TC_Product_020 | SRS-FN-Product-009 | Functional | Fix | Mahmoud
Defect_Product_003 | Error message: "Please login to add items to cart" not dsiplayed when unauthenticated user cannot add product to cart. | User is NOT logged in |  | 1. Open Home page (not logged in) 2. Select a product 3. Set quantity to X 4. Click Add to Cart | invalid | Web Browser (Chrome) |  | Error message: "Please login to add items to cart" | Error message: "Failed to add to cart" |  | Medium | Low | TC_Product_021 | SRS-FN-Product-010 | Functional | Fix | Mahmoud
Defect_Cart_001 | Shipping fees are not added to the total price on the Cart page | 1. Client has a valid account 2. Client is logged in | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Add Product A (x EGP) with quantity 2 (subtotal = x) 2. Add Product B (x EGP) with quantity 1 (subtotal = x) 3. Click on the Cart button 4. Calculate: Total = Sum of subtotals + Shipping fees (x EGP) | valid | Web Browser (Chrome) |  | Total price = sum of(Subtotal) + Shipping Fees Displayed total price value is correct | Total price = sum of(Subtotal) Displayed total price value is correct |  | High | Critical | TC_Cart_006 | SRS-FN-Cart-001 | Functional | Fix | Mahmoud
Defect_Cart_002 | Unwanted Popup message is displayed "Insufficient stock" when click plus (+) button after reach to Max Stock Quantity | 1. Client has a valid account 2. Client is logged in 3. Product is available in stock with quantity above 1 | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Add a product to cart 2. Navigate to Cart page 3. Click plus (+) button repeatedly until reaching stock limit | valid | Web Browser (Chrome) |  | The quantity value stays at max stock quantity and does not exceed the available stock. | The quantity value stays at max stock quantity and does not exceed the available stock. Popup message is displayed "Insufficient stock" |  | Medium | Medium | TC_Cart_010 | SRS-FN-Cart-002 | Functional | Fix | Mahmoud
Defect_Cart_003 | Cart not updated immediately without refresh when click on trach icon with one iteam | 1. Client has a valid account 2. Client is logged in 3. Cart is Empty | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Add a product to cart 2. Navigate to Cart page 3. Click trash icon for that product | valid | Web Browser (Chrome) |  | The selected item is removed from the cart Cart updates immediately without refresh | The selected item is removed from the cart after refresh |  | Medium | High | TC_Cart_011 | SRS-FN-Cart-003 | Functional | Fix | Mahmoud
Defect_Cart_004 | Checkout button is enabled on the Empty Shopping Cart page | 1. Client has a valid account 2. Client is logged in 3. Cart is empty | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Navigate to the cart page | valid | Web Browser (Chrome) |  | Checkout button is disabled on the Shopping Cart page | Checkout button is enabled on the Empty Shopping Cart page |  | Medium | High | TC_Cart_014 | SRS-FN-Cart-004 | Functional | Fix | Mahmoud
Defect_Cart_005 | out-of-stock product still in cart when Product becomes out of stock before checkout | 1. Client has a valid account 2. Client is logged in 3. Product was in stock when added to cart 4. Product becomes out of stock before checkout | 1- Email: gohary@mail.com 2- password: 123456789 3- Email: ganna101@example.com 4- password: 12345689 | 1. Add a product with quantity 1 to cart (stock was available) 2. Navigate to Cart page and note product is visible 3. open with other user and add a product with all quantities 4. click checkout button 5. fill all fields with valid data 6. return to first user 7. Open cart | invalid | Web Browser (Chrome) |  | 1. Out of stock Product is removed from cart 2. Product's subtotal is removed 3. Total price updates correctly | Out of stock Product still in cart |  | Medium | Critical | TC_Cart_018 | SRS-FN-Cart-005 | Functional | Fix | Mahmoud
Defect_Cart_006 | Cart quantity isn't reduced to available stock automatically when Stock decreases before checkout | 1. Client has a valid account 2. Client is logged in 3. Product has stock = X 4. Client added quantity Y to cart (Y ≤ X) 5. Stock decreases to below Y before checkout | 1- Email: gohary@mail.com 2- password: 123456789 3- Email: ganna101@example.com 4- password: 12345689 | 1. Add product with quantity Y to cart (stock was X) 2. Navigate to Cart page and note product is visible 3. open with other user and add a product with all quantities 4. click checkout button 5. fill all fields with valid data 6. return to first user 7. Navigate to Cart page | invalid | Web Browser (Chrome) |  | 1. Cart quantity is automatically reduced to available stock 2. Subtotal and total price update correctly | Cart quantity isn't reduced to available stock automatically |  | Medium | Critical | TC_Cart_019 | SRS-FN-Cart-005 | Functional | Fix | Mahmoud
Defect_Admin_001 | the product data in the admin's product page dosent contain supplier Email | Open URL, Admin is logged in |  | 1.click on actions 2.click add product 3.Enter valid product data 4.Click Save | valid | Web Browser (Chrome) |  | product list is displayed with product name,decription, image ,price quantity,supplier Email for each product | supplier Email dosent appear |  | Medium | Medium | TC-Admin-012 | SRS-FN-Admin-001 | Functional | Fix | jana
Defect_Admin_002 | admin can't add product with all valid data | Open URL, Admin is logged in | product name: jacket photo: dress.jpg description: olive green jacket price:50 : stock avaliability:2 supplier id: 16 | 1.click on actions 2.click add product 3.Enter valid product data 4.Click Save | valid | Web Browser (Chrome) | Product is created | Product is added successfully and redirect admin to dashboard | pop up appear with "please enter valid data" |  | High | critical | TC-Admin-01 | SRS-FN-Admin-001 | Functional | Fix | jana
Defect_Admin_003 | admin can't remove product without validation | Open URL, Admin is logged in | Existing product | 1.click product 2.Select product 3.Click Remove 4.Confirm deletion | valid | Web Browser (Chrome) | Product is deleted | Product is deleted | product didn't deleted and pop up message appear "are you sure? " |  | low | low | TC-Admin-003 | SRS-FN-Admin-002 | Functional | Fix | jana
Defect_Admin_004 | when we add duplicate customer email unexpected message appear | Open URL, Admin is logged in and a customer account with the same email already exists | Existing customer email | 1.click on actions section 2.Click Add user 3.Enter valid Username, existing Email, valid Password, and 4.click on customer radio button 5.Click Save | valid | Web Browser (Chrome) | No duplicate customer account is created | System shows "Email already exists" message and customer account is not created | customer did't added but different pop up message appear "error creating user" |  | Medium | High | TC-Admin-006 | SRS-FN-Admin-003 | Functional | Fix | jana
Defect_Admin_005 | when we add duplicate supplier email unexpected message appear | Open URL, Admin is logged in and a supplier account with the same email already exists | Existing supplier email | 1.click on actions section 2.Click Add user 3.Enter valid Username, existing Email, valid Password, and 4.click on supplier radio button 5.Click Save | valid | Web Browser (Chrome) | No duplicate supplier account is created | System shows "Email already exists" message and supplier account is not created | Supplier did't added but different pop up message appear "error creating user" |  | Medium | High | TC-Admin-009 | SRS-FN-Admin-004 | Functional | Fix | jana
Defect_Admin_006 | admin see in the order page extra details like total and customer email | Open URL, Admin is logged in | Existing order details | 1.Navigate to dashbord 2.click orders 3.validate that all requirments of the order displayed | valid | Web Browser (Chrome) | Lists remain available for review | Order list is displayed with Order ID, Customer Name, and Supplier Name for each order | all points appear with these extra points: total price and reciever |  | medium | Medium | TC-Admin-013 | SRS-FN-Admin-006 | Functional | Not a Bug | jana
Defect_Admin_007 | when admin search with unavalibale product no message appear | Open URL, Admin is logged in | Non-existing product name | 1.click on search bar 2.Enter a non-existing product name in 3.Click Search button | valid | Web Browser (Chrome) | No matching product is displayed | No product found message is displayed | no message appear |  | low | low | TC-Admin-020 | SRS-FN-Admin-008 | Functional | Fix | jana
Defect_Admin_008 | when admin go to add user page , add product page or profile there is navbar and footer in the page | Open URL, Admin is logged in |  | 1-login with admin account 2-go to actions (add user page or add products page )or profile page | valid | Web Browser (Chrome) |  | no navbar and footer in pages | there is navbar and footer in pages |  | low | low |  | wireframe | Functional | Fix | jana
Defect_CHK_001 | Verify successful checkout with valid data (city, Address, Mobile phone of reciever, name's reciever, Email) | open URL User logged in | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Leave City field empty 6. Enter Address 7. Enter phone of reciever 8.Enter name of reciever 9. Click confirm Order button | valid | Web Browser (Chrome) |  | user is redirected to home page and pop up message "Order is placed successfully" | no popup message |  | High | Critical | TC_CHK_001 | SRS-FN- Checkout-001 | Functional | Fix | Mahmoud
Defect_CHK_002 | Verify City field is mandatory when left empty with other valid data | open URL User logged in | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City 6. Leave Address field empty 7. Enter phone of reciever 8.Enter name of reciever 9. Click confirm Order button | invalid | Web Browser (Chrome) |  | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | medium | medium | TC_CHK_003 | SRS-FN-Checkout-002 | Functional | Fix | Mahmoud
Defect_CHK_003 | Verify Address field is mandatory when left empty with other valid data | open URL User logged in | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field 6. Enter Address field 7. Enter phone of reciever 8.leave name of reciever empty 9. Click confirm Order button | invalid | Web Browser (Chrome) |  | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | medium | medium | TC_CHK_004 | SRS-FN-Checkout-002 | Functional | Fix | Mahmoud
Defect_CHK_004 | Verify name of reciever name field is mandatory when left empty with other valid data | open URL User logged in | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field 6. Enter Address field 7. Leave phone of reciever 8.Enter name of reciever 9. Click confirm Order button | invalid | Web Browser (Chrome) |  | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | medium | medium | TC_CHK_005 | SRS-FN-Checkout-002 | Functional | Fix | Mahmoud
Defect_CHK_005 | Verify phone of reciever phone field is mandatory when left empty with other valid data | open URL User logged in | 1- Email: gohary@mail.com 2- password: 123456789 | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field 6. Enter Address field 7. Enter phone of reciever 8.Enter name of reciever 9. Click confirm Order button | invalid | Web Browser (Chrome) |  | pop up message appears "Please Enter the required data" and order is not placed | no pop up message appears "Please Enter the required data" |  | medium | medium | TC_CHK_006 | SRS-FN-Checkout-002 | Functional | Fix | Mahmoud
Defect_CHK_006 | confirmation email isnt' sent to the customer after placing order | open URL User logged in | 1- Email: gohary@mail.com 2- password: 123456790 | 1. Select product from home page 2. Add product to cart 3. Open cart 4. Click checkout 5. Enter City field empty 6. Enter Address field empty 7. Enter phone of reciever 8.Enter name of reciever empty 9. Click confirm Order button | invalid | Web Browser (Chrome) |  | A confirmation email is sent to the customer after successful order placement | A confirmation email isn't sent to the customer after successful order placement |  | High | High | TC_CHK_010 | SRS-FN-Checkout-006 | Functional | Fix | Mahmoud
Defect_Register_001 | Register button missing on Home page, preventing navigation to Register page. | User is on Home page. | N/A | 1.Open the Home page. 2.Click on Register button. | valid | Web Browser (Chrome) | User remains on Register page. | User is redirected to the Register page. | No register button appears on the Home page. User cannot proceed to the Register page. | https://drive.google.com/file/d/18X3AI5RAVKmhGjWW-pHeqd3E1i4jXaer/view?usp=sharing | High | Critical | TC-Register-001 | SRS-FN-REGISTER-001 | Functional | Fix | Fatma
Defect_Register_002 | Incorrect validation error message when registering with an existing email. | 1.User is on Home page. 2.User is navigated to Register page. 3.Email: "fatma@gmail.com" already exists in database. | 1.Username = FatmaYasser2 2.Email = fatma@gmail.com (already used) 3.Password = pass@123 4.Confirm Password = pass@123 5.Role = Customer | 1. Enter valid Username (3–50 characters) 2. Enter the exisiting Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select any role 6. Click Submit | invalid | Web Browser (Chrome) | 1.User remains on Register page. 2. No account is created in the database. | 1.Error message " Email already exists". 2.NO redirect occurs. | 1.Different Error message " Email already registered". and it does not appear under the email field. 2.NO redirect occurs. | EmailErrorMessage.png | Medium | medium | TC-Register-011 | SRS-FN-REGISTER-007 | Functional | Fix | Fatma
Defect_Register_003 | Incorrect validation error message when Username field is left empty on Register page. | 1.User is on Home page. 2.User is navigated to Register page. | 1.leave username field empty 2.Email = fatma008@gmail.com 3.Password = Pass@123 4.ConfirmPassword = Pass@123 5.Role = Customer | 1. Leave username field empty 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select role = Customer 6. Click Submit | invalid | Web Browser (Chrome) | 1.User remains on Register page. 2. No account is created. | 1.Error message: "Username is required" 2.No redirect occurs. | 1.Different Error message: "Required fields missing" 2.No redirect occurs. | https://drive.google.com/file/d/13ORsURVit0JUMX43akfoWn1r7CCkKt2e/view?usp=sharing | Medium | Medium | TC-Register-018 | SRS-FN-REGISTER-001, SRS-FN-REGISTER-004 | Functional | Fix | Fatma
Defect_Register_004 | Incorrect validation error message when Password field is left empty on Register page. | 1.User is on Home page. 2.User is navigated to Register page. | 1.Fatma 2.Email = fatma882@gmail.com 3. Leave password field empty 4.Confirm password=pass@123 5.Role = Customer | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Leave password field empty 4.Enter valid confirm Password (8–64 characters) 5. Select role = Customer 6. Click Submit | invalid | Web Browser (Chrome) | 1.User remains on Register page. 2. No account is created. | 1.Error message: "Password is required" 2.Error message: "Password and Confirm Password do not match" under confirm password field 3. no redirect occurs. | 1.Different Error message: "Required fields missing" under password field 2.Error message: "Password and Confirm Password do not match" under confirm password field 2.No redirect occurs. | https://drive.google.com/file/d/1ot78rbpIzH4H4rMzaInFFGzTDDt2FIyh/view?usp=sharing | Medium | Medium | TC-Register-019 | SRS-FN-REGISTER-001, SRS-FN-REGISTER-005 | Functional | Fix | Fatma
Defect_Register_005 | Incorrect validation error message when Confirm Password field is left empty on Register page. | 1.User is on Home page. 2.User is navigated to Register page. | 1.Fatma 2.Email = fatma882@gmail.com 3.Password=pass@123 4.Leave confirm Password field empty 5.Role = Customer | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3.Enter valid Password (8–64 characters) 4. Leave confirm password field empty 5. Select role = Customer 6. Click Submit | invalid | Web Browser (Chrome) | 1.User remains on Register page. 2. No account is created. | 1.Error message: "Confirm Password is required" 2.No redirect occurs. | 1.Different Error message: "Required fields missing" 2.No redirect occurs. | https://drive.google.com/file/d/1uIOEUw3quvDq-jX8967PwN8YU6Y11eSH/view?usp=sharing | Medium | Medium | TC-Register-020 | SRS-FN-REGISTER-001, SRS-FN-REGISTER-005 | Functional | Fix | Fatma
Defect_Register_006 | Incorrect validation error message when Email field is left empty on Register page. | 1.User is on Home page. 2.User is navigated to Register page. | 1.Fatma 2.LeaveEmail field empty 3.Password =pass@1234 4.Confirmation Password = pass@1234 5.Role = Customer | 1. Enter valid Username (3–50 characters) 2. Leave Email field empty 3. Enter valid Password (8–64 characters) 4. Enter matching confirm Password 5. Select role = Customer 6. Click Submit | invalid | Web Browser (Chrome) | 1.User remains on Register page. 2. No account is created. | 1. Error message: "Email is required" 2.No redirect occurs. | 1.Different Error message: "Required fields missing" 2.No redirect occurs. | https://drive.google.com/file/d/1cDCIk-fvM8JlHgNSVazLM_V3xhr4ng_R/view?usp=sharing | Medium | Medium | TC-Register-021 | SRS-FN-REGISTER-001, SRS-FN-REGISTER-005 | Functional | Fix | Fatma
Defect_Register_007 | Unwanted success message appears after successful registration. | 1.User is on Home page. 2.User is navigated to Register page. | 1.Username = FatmaYasser 2.Email = fatma@gmail.com 3.Password = Pass@123 4.Confirm Password = Pass@123 5.Role = Customer | 1. Enter valid Username (3–50 characters) 2. Enter unique Email 3. Enter valid Password (8–64 characters) 4. Enter matching Confirm Password 5. Select role = Customer 6. Click Submit | valid | Web Browser (Chrome) | 1.User is on Login page. 2.Account is created in the database. | User is redirected to Login page. | 1.A success message appears: "Registration successful! Redirecting..." 2.User is redirected to Login page. | https://drive.google.com/file/d/14C-r5BbPf7IuE1yCTd1cWUJ21ttq1AfE/view?usp=sharing | Medium | Low | N/A | N/A | Functional/UI | Fix | Fatma
Defect_Login_001 | Login button missing on Home page, preventing navigation to Login page. | User is on Home page. | N/A | 1.Open the Home page. 2.Click on Login button. | valid | Web Browser (Chrome) | User remains on Login page. | User is redirected to the Login page. | No login button appears on the Home page. User cannot proceed to the Login page. | https://drive.google.com/file/d/18X3AI5RAVKmhGjWW-pHeqd3E1i4jXaer/view?usp=sharing | High | Critical | TC-Login-001 | SRS-FN-login-001 | Functional | Fix | Fatma
Defect_Login_002 | Missing validation error for empty Password field when both Email and Password are empty on Login page. | 1.User is on Home page 2.Navigated to Login page | 1. Leave Email empty 2. Leave Password empty | 1. Leave Email empty 2. Leave Password empty 3. Click Submit | invalid | Web Browser (Chrome) | User remains on Login page. Not logged in. | 1.Error message: "Email is required" and "Password is required" 2. No redirect occurs | 1.Only one Error message: "Email is required" appears 2. No redirect occurs | https://drive.google.com/file/d/12Ke8u2BXz712HyRr6mBc9yKpeIl4C9NG/view?usp=sharing | High | Medium | TC-Login-010 | SRS-FN-login-001, SRS-FN-login-004 | Functional | Fix | Fatma
Defect_Landing_001 | Profile buttons still visible instead of Login/Sign-up button. |  | url http://localhost:5000/ | open URL for landing page | valid | Web Browser (Chrome) |  | Both "Login" and "Sign-up" buttons/links are visible in the navigation bar | Profile buttons still visible instead of Login/Sign-up button. |  | High | Critical | TC_Landing_001 TC_Landing_002 TC_Landing_003 | SRS-FN-Landing-001 | Functional/UI | Fix | Mahmoud
Defect_Landing_002 | Add to Cart button shows a error message "Failed to add to cart" instead of "Please login to add items to cart" |  | url http://localhost:5000/ | open URL for landing page Click on the "Add to Cart" button. | valid | Web Browser (Chrome) |  | A message appears: "Please login to add items to cart" | A message appears: "Failed to add to cart" |  | Medium | Low | TC_Landing_004 | SRS-FN-Landing-001 | Functional | Fix | Mahmoud
Defect_Landing_003 | unauthenticated user redirected to /customer/ instead of login when click on Home Button |  | url http://localhost:5000/ | open URL for landing page Ensure user is logged out. Click on the "Home" button. | valid | Web Browser (Chrome) |  | User is redirected to the Login page. | redirected to /customer/ |  | Medium | Medium | TC_Landing_005 | SRS-FN-Landing-001 | Functional | Fix | Mahmoud
Defect_Landing_004 | unauthenticated user redirected to /customer/cart instead of login when click on Cart Button |  | url http://localhost:5000/ | open URL for landing page Ensure user is logged out. Click on the "Cart" button. | valid | Web Browser (Chrome) |  | User is redirected to the Login page. | redirected to /customer/cart |  | Medium | Medium | TC_Landing_006 | SRS-FN-Landing-001 | Functional | Fix | Mahmoud
Defect_Landing_005 | unauthenticated user redirected to /customer/orders instead of login when click on Orders Button |  | url http://localhost:5000/ | open URL for landing page Ensure user is logged out. Click on the "Order" button. | valid | Web Browser (Chrome) |  | User is redirected to the Login page. | redirected to /customer/orders |  | Medium | Medium | TC_Landing_007 | SRS-FN-Landing-001 | Functional | Fix | Mahmoud
Defect_Supplier_001 | uncorrect validation message when supplier missing required fields on add product page | Open URL, Supplier is logged in |  | 1.Click on Add Product 2.Leave one or more required fields empty 3.Click Submit | invalid | Web Browser (Chrome) |  | System shows validation message "please enter the required data" and product is not submitted | System shows "Enter Valid Data" instead of "please enter the required data" |  | Medium | Medium | TC_Landing_007 | SRS-FN-Supplier-001 | Functional | Fix | Ganna Adel
count
37
open
0
fix
37
not a bug
1